## KPI UNPACKING FRAMEWORK
THEMES | KPI No. | KEY PERFORMANCE INDICATORS | Sub-KPI | ACTION PLAN
[5 empty] | WEIGHTAGE (as per CA) | Deliverables to be Completed by EMO | Evidence of Completion of Deliverables | Timeline for Completion of Deliverables by EMO | Mode of Submission/Reporting to IE and Deadlines | Verification by IE | Comments
Management and Organization: Planning, Implementation & Evaluation | 1 | School Management Plan | 1.1 | Annual Management Plan (AMP) | 08 Marks | 1. Conduct baseline survey and associated activities (inventory / infrastructure status) 2. AMP (for each school listed in the Package) 3. Implementation Timelines (activities disaggregated by quarter, and ideally presented in the form of a Gantt chart) | 1. Baseline report including following details: - records of movable and immovable assets, books, resources, machinery, furniture, fixtures, equipment, etc, students, teachers, staff, compliance (Section 7, pg.29) - Availibility of EMIS - Staff availibility (teaching/non-teaching) status - Staff attendance (teaching/non-teaching) status - Students enrollment, attendance and retention status - Use of Lesson planning/SoS - Assessment procedure - TNA - Repair and Maintenance - Availibility of SMC - PTMs - Health screening - Sports/co-curricular actviities 2. AMP document for each individual school 3. Implementation Timelines for each individual school | In Y1: Baseline & AMP, For the first year of the Concession Period, within 90 (calendar) days of the effective date Baseline (Y1 only) Y2 onwards: AMP + SIP - For subsequent years, 30 days prior to the start of the academic year. By 1st August 20XX. The current academic year is August to July As per Section 7, pg. 30 of the Concession Agreement: The first two KPI report will not impact the Annuity Payments, but deadlines for completion and submission of deliverables (such as AMP, IF Timelines, Annual SoS, Baseline Surveys) are strict | Baseline : via email. Upon development of AMP/SIP: via email. This submission is to thereafter be reported in Q1's Quarterly Progress Report. | Desk-based review of AMP IE also visits usually at the start of IE agreement and and therefater regulary for Quarterly Verification Report. | i. Deadlines established based on Academic Year running from 1st August to 31st July ii. Each school under RFP 6 may have a different strategy and AMP/SIP, based on baseline conducted (same principle applies for Y2 onwards) iii. EMO is required to maintain records (in both soft and hard copies) of all moving and immovable assets including (but not limited to) books, resources, machinery, furniture, fixtures, equipment etc., and students, teachers, staff, and compliance with KPIs (Section 7, pg. 29, Concession Agreement). Initial stock-take should be made part of the Baseline, to be conducted at all schools under the Concession. vi. AMP will be approved by IE (if requied a revised AMP will requested by the EMO, depending on the desk based review.) vii. EMO needs to ensure that during development it should take into considration, the commitments from CA, KPIs, Technical and financial proposal. (Annexures of the SMB technical proposal: School and classroom observation checklist, Academic Calender, and HR Policy). viii. Dates may change according to SMB effective date: XX September 2021
[6 empty] | 1. AMP to be developed with activities shared quarterly for Y1. 2. Status of completion of quarterly activities in tabular format Q2 / Y1 and Y2 onwards (mentioned in the AMP and Implementation Timelines) and status sharing for each activity. | Evidence for completion of all tasks/activities referred to in the AMP/Implementation Timelines, and may include: 1. Field Reports 2. Activity Completion Reports 3. Photographs (ideally with timestamps) 5. Participnats list 6. Minutes of meetings 7. Govt. Notifications etc. 8. Others | Ongoing Y1 onwards - 15 days of close of an academic quarter as part of the QPR. Report status of the AMP/SIP/IT activities as per the gantt chart at the end of each quarter. This is shared as part of the Quaterly Progress Report | Updates on completion of quarterly activities to be provided in a given academic quarter's Quarterly Progress Reports (QPR) EMO Evaluation Quarter Periods based on CA Y1 Q-1 - XX September 2021 (effective date) - XX Q-2 - Q-3 - Q-4 - (Reporting deadlines or submisison of report may change based on Section 7, pg. 29, wherein EMO is required to report within 15 days of close of an academic quarter. | Tracking/monitoring and verification of activities identified in the AMP, reconfirmed in the Quarter (Start) Meeting between the IE and the EMO, and report/evidence provided by the EMO in its Quarterly Progress Reports. Field visits after quarterly report. Field visits during the quarter for activities such as PTMs, Sports day , staff trainings, Assessments etc. | i. Implementation Timelines will be provided in a Gantt chart, disaggregated at (at least the quarterly level). ii. Most activities mentioned in the AMP and implementation timelines will be covered in one of the subsequent KPIs/sub-KPIs. The EMO may report these activities (and their required evidence) under those specific KPIs/sub-KPIs in its Quarterly Progress Report. iii. In addition to the Quarter (Start) Meeting (where activities expected to be completed during the course of the quarter are discussed), the EMO is requested to intimate the IE about the specific date of those activities (such as PTMs, sports days, assessments, staff trainings etc.) at least 4 to 5 days prior, so that the IE's field staff can be mobilized for observation visits. iv. Section 8, pg. 33-34: Within fifteen (15) days of Annuity Amount Payment Evaluation Date, the EMO will submit the QPR to the IE. The IE will issue verified evaluation report within the next fifteen (15) days to the IA. v. In academic quarters where submission of AMP is due, the allocated marks for this KPI will be bifurated as follows: 04 marks for development and submission of AMP for the upcoming academic year, and 04 marks for implementation of current year's/applicable AMP. In the remaining three academic quarters, the entire 08 marks will be allotted towards implementation of AMP and its activities.
|  |  | 1.2 | Implementation Framework | 04 Marks | 1. Implementation Framework | 1. Implementation Framework/School Manual | In Y1: Within 15 (calendar) days of submission of AMP Y2 onwards: (Within 15 (calendar) days of submission of AMP for subsequent years) | Upon development of Implemetation Framework/School Manual: via email This submission is to thereafter be reported in Q1's Quarterly Progress Report. | Desk-based review of Implementation Framework/School Manual | i. The School Manual will contain the EMO's standardized policies and SOPs for all schools (e.g. admission policy, student and teacher attendance tracking mechanisms, student assessment policies, health and safety policies and activities etc), as well as plans, procedures and protocols for activities/tasks envisaged under the following KPIs/sub-KPIs. Other plans if as per Technical Proposal: Annual Stakeholders Engagement Plan. ii. Tentative activities for a given quarter will be shared with IE in the Quarter (Start) Meeting (i.e. a meeting at the start of the quarter), and actual dates of activities with be shared with IE at least one (01) week prior to the activity(s). iii. The Implementation Framework will include a Safety and Surveillance Program/Safety Regulations (see Section 7, pg. 27, Concession Agreement)
[6 empty] | 1. Adherence to SOPs stipulated in Implementation Framework/School Manual in the completion of quarterly activities | Evidence of adherence to SOPs stated in Implementation Framework/School Manual may include: 1. Completed standardized forms (e.g. JDs and Candidate Evaluation Form for hiring of school staff, duly completed Student Enrolment/Dropout Forms, survey tools for TNA, etc.) 2. Relevant datasets 3. Photographs 4. Others | ONGOING: Completion of quarterly activities (mentioned in AMP and Implementation Timelines) during the course of the relevent academic quarter (as per Implementation Timeline). | Updates on completion of quarterly activities as per established protocols to be provided in a given academic quarter's Quarterly Progress Reports | Tracking/monitoring and verification (at the field and/or head office level) of processes employed for activities identified in the AMP and Implementation Timelines Review of report/evidence provided by the EMO in its Quarterly Progress Reports. | i. During its verification for this KPI, the IE may visit the school and/or the Head Office and request to see and review duly completed documents pertinent to the activity completed. Ii. Duly developed Implementation Framework/School Handbook, and all associated guidelines, forms, and data collection tools which are required for implementation of activities
|  |  | 1.3 | Development of an EMIS and Functioning of the EMIS | 05 Marks | 1. Development and deployment of EMO's EMIS system at the school level/Educational software installation & implmentation EMO's EMIS system comprises Teachers and students profiling & database , HR database, Learning, Infrastructure, Financial, Inventories, Library, Monitoring, Health. 2. Report/update on maintenance and functioning of EMIS system. Summary of EMIS of all schools listed in the package will be included in each quarterly report. The EMO shall mandatorily upload/ maintain/ provide necessary data as required. | 1. Narrative update on development of EMIS (if EMIS is under development) 2. Narrative update on maintenance and functioning of EMIS 3. Screenshots/ Summary of EMIS dash board/summary pages. IE to review EMIS. | Development/Deployment of EMIS Within 180 days of Effective Date, thereafter reporting on functioning on quarterly basis | Reporting of development and deployment of EMIS to be reported in Y1Q1's Quarterly Progress Report Updates on functioning and maintenance of EMIS to be provided in a given academic quarter's Quarterly Progress Reports | Quarterly review of EMIS including cross-verifying databases/datasets updated thereon; On-field verification (quarterly) in terms of the use of the EMIS at the school level, by the IE's field personnel. Review of EMIS by IE (through log in or at EMO's office) | i. The narrative in the Quarterly Progress Reports will provide an update on the development, implementation/deployment, and functioning of the EMIS (SMS and SMA) system. ii. If possible, the EMO will grant the IE user access to the EMIS portal once it is deployed (only viewing or downloading necessary informaation). iii. If the EMO already has a functional EMIS deployed at other schools, the same EMIS may be used, and relevant school information be uploaded thereon.
| 2 | Improved Staff Availability and Attendance | 2.1 | Improvement in staff attendance and Functional Attendance Management. | 05 Marks | 1. Functional staff attendance management (i.e. due recording and monitoring of staff attendance, leaves, and absenses on hard-copy staff attendance registers and/or biometric machines as committed by the EMO. 2. Updating of staff attendance, leaves, and absenses on EMIS 3. Improvement in staff attendance from previous quarter | 1. Raw database of biometric staff attendance of each of the schools 2. Monthly staff attendance percentages of each of the schools 3. Improvement in staff attendance as compared to the previous quarter 4. Narrative on any reasons/justifications e.g. in cases of low staff attendance, or no improvements in such attendance 5. Narrative on any challenges faced in maintaining or increasing staff attendance 6. Narrative on any change in process of recording daily staff attendance (as compared to the School Manual) implemented during the quarter. | ONGOING: Recording and monitoring of staff attendance, leaves, and absenses during the course of the relevant academic quarter | Staff attendance statistics to be provided in a given quarter's Quarterly Progress Reports Relevant datasets to be attached as annexures to Quarterly Progress Reports: | On field verification of: 1. Updating of staff attendance register 2. Use of biometric machines 3. Updating of staff attendance Desk-based verification of: 4. Staff attendance statistics provided in Quarterly Progress Reports, against datasets provided by the EMO and those obtained from the field by the IE | i. To reduce issues during verification (which may delay issuance of Quarterly Verification Certificates by the IE), and for the EMO's own effective internal monitoring, it is advised that systematics checks be set at the school and central level to ensure that staff attendance as recorded on (a) school registers (b) biometric machines, and (c) EMIS are reconciled prior to quarterly reporting. ii. Leave manual and system may be introduced in accordance with Authority's existing and evolving instructions.
|  |  | 2.2 | Availability of Staff | 03 Marks | 1. Ensuring availability of qualified teaching, non-teaching and technical staff in each school for all grades and subjects and administrative, operational during the academic year. 2. Hiring of teaching/non-teaching staff, as per the EMO's Financial/Technical Proposal, following due process mentioned in Implementation Framework/School Manual: - Core project team will include 1 of each; Project Director, Compliance Manager, Executive District Coordinator, Education Expert and Finance Expert. JD: EMO project implementation and research with Project Director* *Project Director will look after the core teams daily progress and reporting. PD will act as a liason between other parties and EMO. - School based staff: 64 teaching staff, positions include: ECE, HST, PST, IT Instructor, PTI, Handyman Instructor, Trainee Teacher; 28 Non-teaching staff, positions include: Admin Assistant, Cleaning Staff, Watchman, Nurse, Gardener, EMI and Web Developer - Private teaching staff will include teachers for Math, IT, Art, Science and English - Grouped schools will have 1 newly inducted teacher 3. Updating relevant staff databases on EMIS | 1. List of teaching/non-teaching staff hired in a given academic quarter, including associated duly completed standardized forms (e.g. Candidate Evaluation Form, JD, and Employment Contract) 2. Updated complete list of all teaching/non-teaching staff (appointed by SELD and the EMO) including their designation, start date, end date (for e.g. in case of resignations, transfers, etc.) as at the end of a given academic quarter | ONGOING: Hiring of staff as stipulated in AMP/SIP, Implementation Timelines and Financial/Technical Proposal | Staff hiring and turnover statistics to be provided in a given academic quarter's Quarterly Progress Reports Databases/lists to be attached as annexures to Quarterly Progress Reports | On field verification of: 1. Availability of teachers hired as evidenced in entries on the Master Roll 2. Hiring of teachers as per EMO's Technical Proposal. | 1. Important Note: The EMO is advised to include information regarding the number of teaching/non-teaching staff designated for the school as per SNE (Sanctioned positions), the staff available at the school at the time of handing over, and the number of staff hired, staff committeed in proposal . This will allow the EMO to shed light on the availability of teachers in cases where for e.g. the SNE was not complete and the EMO had to hire additional teachers to address the issue. 2. Section 7, pg. 30: The EMO is required to appoint a Compliance Manager/Contract Manager, as per the requirements set out in Annex 1, Concession Agreement. Responsibility: ensure EMO complies outside regulatory requirments/internal policies/abides by KPIs, terms and conditions, Scope of work in CA. 3. Section 7, pg. 31: EMO will ensure key staff is employed on the effective date. If Key staff changes then EMO will prior approval from SELD, replacement has to have same qualification, experience and expertise. Key Staff: Project Director, Compliance Manager, Executive District Coordinator, Education Expert, and Finance Expert.
| 3 | Improved Students' Enrolment, Attendance and Retention | 3.1 | Students Enrolment, Attendance Management and Retention Plan | 02 Marks | Development of: 1. Student Enrolment Plan 2. Student Attendance Management Plan 3. Student Retention Plan (These Plans may be annexed to the overall AMP/SIP) | 1. Formally approved Student Enrolment Plan 2. Formally approved Student Attendance Management Plan 3. Formally approved Student Retention Plan | In Y1: Within 60 (calendar) days of handing over of school. Y2 onwards: Along with AMP/SIP | Upon development of Plans: via email. This submission is to thereafter be reported in Q1's Quarterly Progress Report. | Desk-based review of Plans, in light of the Baseline Survey, and targets stipulated in the Concession Agreement. | i. Student Enrolment Plan should be developed in light of Baseline conducted by the EMO, as well as maximum capacity (disaggregated by grade); should also focus on girl's enrolment ii. Student Retention Plan will be influenced by the EMO's community mobilization and outreach strategy. Retention refers to individual/unique students graduating from one grade to the next (or in the case of terminal grades, either graduating or repeating the grade (but nevertheless remaining in school) iii. A student who absent for ninety (90) days without any prior notice or reasonable cause will be considered dropped-out
|  |  | 3.2 | Improvement in Student Enrolments, Attendance, Retention Rates, benchmarked with baseline | 08 Marks | Student enrolment, attendance and retention targets as stipulated in Annex-II, Concession Agreement (mentioned in the comments) 1. Due recording and monitoring of student attendance, leaves, and absenses on hard-copy staff attendance registers 2. Updating of student attendance, leaves, and absenses on EMIS 3. Internal verification and data cleaning of student attendance record | 1. Student enrolment (including drop-outs) and attendance data, disaggregated by grade (MS Excel sheet extracted from EMIS) for each school 2. Changes (i.e. increase/decrease) in student enrolment monthly, thereby identifying any new enrolments and/or dropouts, benchmarked to student enrolment at baseline. 3. Monthly student attendance percentages of each of the schools, disaggregated by grade and gender (along with screenshots of EMIS ) 4. Improvement in student attendance as compared to the previous quarter 5. Student retention, as compared to the previous quarter 6. Narrative on any reasons/justifications e.g. in cases of low student attendance, or no improvements in such attendance, high drop-outs, etc.) 7. Narrative on any challenges faced 8. Narrative on any change in process of recording daily student attendance (as compared to the School Manual) | ONGOING: Recording and monitoring of student enrolment (and drop-out), attendance (incl. leaves and absenses) during the course of the relevant academic quarter | Student enrolment/drop-out and attendance statistics to be provided in a given academic quarter's Quarterly Progress Reports Databases/lists to be attached as annexures to Quarterly Progress Reports | On field verification of: 1. Updating of student attendance registers 2. Updating of student attendance data on the EMIS 3. Updating of GR Desk-based review of achievement of enrolment, attendance, and retention targets. | i. To reduce issues during verification (which may delay issuance of Quarterly Verification Certificates by the IE), and for the EMO's own effective internal monitoring, it is advised that systematic checks be set at the school and at the central level to ensure that student attendance is recorded timely on school registers. ii. Annual enrolment targets for Main Schools: a) Baseline student classroom ratio + 5% increase for Assessment Year 1 b) Baseline student classroom ratio + 10% increase for Assessment Year 2 and so on until 40 students per classroom attained iii. Annual enrolment targets for Grouped Schools: a) Baseline student classroom ratio + 2% increase for Assessment Year 1 b) Baseline student classroom ratio + 5% increase for Assessment Year 2 and so on until 40 students per classroom attained iv. Annual attendance targets for Main school a) 90% aggegate attendance with 75% indiviual attendance in 1st Assessment Year b) Thereafter, min 2% annual increase till optimum attendance rate is reached v. Annual attendance targets for Grouped school a) 80% aggegate attendance with 75% indiviual attendance in 1st Assessment Year b) Thereafter, min 2% annual increase till optimum attendance rate is reached vi. Annual retention rate for Main schools: 5% increase from baseline annually till optimum low drop-out is attained vii. Annual retention rate for Grouped schools: 3% increased from baseline annually till optimum low drop-out is attained
Learning and Teaching | 4 | Lesson Planning and Students' Assessment System | 4.1 | Annual Scheme of Studies | 05 Marks | 1. Development of yearly Annual Scheme of Studies 2. School Class wise Syllabus will be developed, aligned with the Provincial Curriculum of Pakistan 3. Implementation of Annual Scheme of Studies by teaching staff for all grades. | 1. Annual Scheme of Studies 2. Report on Implementation of Annual Scheme of Studies | In Y1: Within 90 (calendar) days of handing over (i.e. along with AMP/SIP) Y2 onwards: (Along with AMP/SIP) ONGOING: Implementation of Annual Scheme of Studies during the course of the relevant academic quarter. | Upon development of Annual Scheme of Studies: via email. This submission is to thereafter be reported in Q1's Quarterly Progress Report. Report on Implementation to be provided in Quarterly Progress Report | Desk-based review of Scheme of Studies, in light of the Baseline Survey, and requirements of the Concession Agreement On field verification by matching Annual Scheme of Studies with lessons being taught by teachers in given week.
|  |  | 4.2 | Lesson planning system (Curriculum and Syllabus) | 10 Marks | 1. Lesson Plan Templates 2. Lesson planning (using aforementioned Templates) by all teaching staff As per technical proposal: - Students’ extra-curricular activities and STEAM (Science, Technology, Engineering, Art and Math) will be incorporated in lesson planning | 1. Standardized Lesson Plan Template 2. Samples of lesson plans developed by teaching staff during the course of the academic quarter | Within 30 days of the effective date, thereafter quarterly reporting ONGOING: Development of lesson plans during the course of the relevant academic quarter | Updates on development and use of lesson plans to be provided in a given quarter's Quarterly Progress Reports Samples of lesson plans to be attached as annexures to Quarterly Progress Reports | On-field verification of development and use of lesson plans by teachers (as per Annual Scheme of Studies) by IE field personnel Classroom observations and informal interviews with teaching staff
|  |  | 4.3.1 | Improved student learning and achievement | Formative Assessments: 05 Marks in Q2-Q4 and 10 Marks in Q1 | 1. Conducting of FORMATIVE assessments/As per technical proposal: Monthly formative assessments 2. Updating of students' academic records (data of formative assessment) on EMIS | 1. Formally approved schedule of formative assessment conducted during the quarter, disaggregated by grade 2. Samples of student answer scripts 3. Dataset of student scores acheived, disaggregated by grade and subject | ONGOING: Scheduling, planning and implementation of formative assessments during the course of the relevant academic quarter (as stipulated in Implementation Timelines) | Student performance and competency statistics to be provided in a given academic quarter's Quarterly Progress Reports Databases/lists to be attached as annexures to Quarterly Progress Reports | On-field verification of formative assessments (observation) | Improved student learning and achievement: i. Formative Assessments: 05 marks in Q2-Q4 and 10 marks in Q1 Students achieveing a level of competence in their subjects in each grade progressively. ii. For Main Schools: 4% increase from baseline in 1st Year of CA, and then maintaining 5% increase in succeeding years iv. For Grouped Schools: 3% increase from baseline in 1st Year of CA, 4% increase in Y2, 5% increase in Y3, and then maintaining 5% increase in succeeding years
|  |  | 4.3.2 |  | (In house) Summative Assessments: 05 Marks in Q4 | 1. Conducting of (IN HOUSE) SUMMATIVE assessments - School based assessment 2. Updating of students' academic records on EMIS 3. Achievement of student competency targets as stipulated in Annex-II, Concession Agreement (School based annual assessment data of grade KG to 8 along with percentage and comparative ratio with previous year) | 1. Formally approved schedule of summative assessment conducted during the quarter, disaggregated by grade 2. Samples of student answer scripts 3.Student performance/acheivement in formative assessment, disaggregated by grade and subject (MS Excel sheet extracted from EMIS (SMS/SMA) 4. Student competency statistics, disaggregrated by grade and subject. In final academic quarter, additional focus on: 5. Comparartive statistics of student performance/acheivement and competency, compared to the previous academic year | ONGOING: Scheduling, planning and implementation of in-house summative assessments during the mid term and final academic quarter. So reporting twice for mid-term and final exams (as stipulated in Implementation Timelines) | Bi annual reporting Databases/datasets to be attached as annexure to Quarterly Progress Reports Only in Q2 and Q4 | On-field verification of: 1. Summative assessments (observation) 2. Sampled based cross verification of hard-copy student answer scripts and information contained in submitted soft-copy datasets. | i. (In house) Summative Assessments: 05 marks in Q4 Students achieveing a level of competence in their subjects in each grade progressively. ii. For Main Schools: 4% increase from baseline in 1st Year of CA, and then maintaining 5% increase in succeeding years iii. For Grouped Schools: 3% increase from baseline in 1st Year of CA, 4% increase in Y2, 5% increase in Y3, and then maintaining 5% increase in succeeding years
|  |  | 4.3.3 |  | (External) Summative Assessments: 05 Marks in Q2 | 1. Conducting of (EXTERNAL) SUMMATIVE assessments - SAT/Board Exams 2. Updating of students' academic records on EMIS 3. Achievement of student competency targets as stipulated in Annex-II, Concession Agreement | In second academic quarter, additional focus on: 1. Formal student marksheets shared by SELD/RSU with the EMO, for each school 2.Student performance/acheivement in summative assessment, disaggregated by grade and subject (MS Excel sheet extracted from EMIS (SMS/SMA) 3. Student competency statistics, disaggregrated by grade and subject. 4. Comparartive statistics of student performance/acheivement and competency, compared to the previous academic year | As per timelines stipulated in relevant SELD notifications | Annual reporting Databases/datasets to be attached as annexure to Quarterly Progress Reports | Review of SAT/board result marksheets and cross-verification against MS Excel sheet dataset on student performance and competency. | i. External summative assessments (specifically SAT examinations for Grades 5 and 8 are expected to be conducted by the SELD in the final academic quarter. However, reporting of student achievement and competency (in the EMO's Quarterly Progress Reports) is only required in Q2. ii. 05 marks in Q2 iii. For Main Schools: 4% increase from baseline in 1st Year of CA, and then maintaining 5% increase in succeeding years iv. For Grouped Schools: 3% increase from baseline in 1st Year of CA, 4% increase in Y2, 5% increase in Y3, and then maintaining 5% increase in succeeding years
|  |  | 4.3.4 |  | Sample based annual assessment by IE: 05 Marks in Q3 | 1. Development of overarching Academic Assessment Plan by IE 2. Conducting Independent Assessment at the start of the Concession Thereafter, 3. Conducting annual Independent Academic Assessment, in Q3 (Note: Please see comments) | 1. Approved Academic Assessment Plan 2. Testing tools and templates 3. Student answer scripts 4. Data entry and cleaning 5. Report of student performance and competency | In Y1: 1. Initial academic assessment within 30 (calendar) days of school handing over 2. Yearly end-of-year student assessment in Q3 Thereafter: 3. Yearly end of year student assessment in Q3 | Not applicable | Not applicable | i. This activity is to be conducted by the IE, and will be reported in the IE's Quarterly Verification Report for Y1Q1 (student academic baseline) and thereafter, in Q3/4 of subsequent academic years (student performance). ii. 05 marks in Q3 iii. For Main Schools: 4% increase from baseline in 1st Year of CA, and then maintaining 5% increase in succeeding years iv. For Grouped Schools: 3% increase from baseline in 1st Year of CA, 4% increase in Y2, 5% increase in Y3, and then maintaining 5% increase in succeeding years
| 5 | Continuous Professional Development (CPD) of Staff | 5.1 | Training Need Assessment (TNA) | 05 Marks | 1. TNA tools and templates 2. Due conduct of TNA - teaching and non-teaching 3. TNA Reports (for each school of Package), including identified training needs (academic and management-related) 4. CPD Plan/Training Plan based on TNA - teaching & non-teaching (Note;: Please see comments) | 1. TNA Report (including TNA tools/template, TNA methodology, and results/findings.) 2. Formally approved TNA Report and CPD Plan | In Y1: Within 60 (calendar) days of handing over Y2 onwards: Within Q1 | Annual reporting Databases/datasets and documents to be attached as annexure to Quarterly Progress Reports | 1. Desk-based review of TNA tools, TNA Report, and CPD Plan 2. On-field verification of TNA (observation) | i. TNAs are to be conducted in the first quarter of a given academic year ii. The TNA should be conducted as per the requirements stipulated in Annex IV and specifically, the National Professional Standards for Teachers in Pakistan (NPSTP) 2009.
|  |  | 5.2 | Continuous Professional Development Trainings | 10 Marks | 1. Implementation of CPD Plan, and execution of CPD training sessions during school vacations Section 7, page 32: Conduct (2) training sessions each of at least 18 hours for each employee, particularly teaching staff in each financial year. As per Technical Proposal: - 150 hours of training/coaching in a year during the first five years at SMB Teachers Training Institutes; ICT-based trainings - 5 day induction training - Refresher sessions - Weekly/Monthly, every Sat, at TTI - Annual trainings (1-2 weeks) - Classroom observation-based coaching/training will be provided to teachers by SMB admin staff and Head Masters. 2. Updating teaching & non-teaching staff records on EMIS | 1. Formally approved CPD Training Reports (including attendance list, materials used, and total training hours) 2. Number of trainings conducted, and training hours (cumulative) of each schools' staff as per the CPD Plan, as per TNA report, budgeted trainings and additional trainings. | In Y1: (At least) One (01) CPD session within the academic year Y2 onwards: During school vacations (winter, summer), bi-annual trainings | In Y1: Reporting on training in the academic year till Q4 (atleast 1 CPD session) Thereafter, bi-annual reporting (twice a year) - Summer/Winter Vacations Databases/datasets and documents to be attached as annexures to Quarterly Progress Reports | 1. Desk-based review of Training Report 2. On field verification of CPD training sessions (observations by IE's field staff) | i. The EMO is required to conduct at least two (02) trainings, each of 18 hours for each employeee in each academic year (see Section 7, page 32, Concession Agreement) ii. All teacher trainings should be ideally scheduled during school vacations (and should not exceed sixty (60) hours in aggregate). Any trainings scheduled in times other than vacations should result in only minimum disruption of teaching and other Services (see Section 7, pg. 32, Concession Agreemment) iii. Section 7, pg. 32: The EMO will share the Training schedue thirty (30) days prior to the start of such training(s) with all Parties iv. Section 7, pg. 32: The Operator shall ensure that all teacher Trainings are scheduled during the Vacations; provided that any Trainings scheduled during the Vacations should not exceed sixty (60) hours in aggregate; provided further that if any teacher Trainings are required to be conducted during a period other than the Vacations, the Operator shall ensure that there is minimum disruption to the Services.
|  |  | 5.3 | Quality Assurance of CPD |  | 1. QA Observation Tool 2. Conducting classroom/office work observations (after conduct CPD trainings, as per CPD Plan) 3. QA Reports, as per QA strategy developed - QA reports of trained staff based on classroom teaching practices and office and academic management on bi-annual basis (in following quarter after each CPD training is conducted). | 1. Templates of QA Observation Tool 2. Duly completed QA Observation Tools for school staff trained 3. QA Reports | Academic quarter following the quarter when CPD sessions were conducted. | Bi-annual reporting (twice a year) / or as per the trainings delivered / CPD plan | 1. Desk-based review of QA Report 2. On-field verification of findings of QA Report in following academic quarter, through observations and short interviews with staff.
School Repair and Maintenance and Improved Community Engagement | 6 | School Reapir and Maintenance and Improved Community Engagement | 6.1 | Repair and Maintenance Plan of all the schools listed in the Package including infrastructure, equipment, furniture and fixtures | 06 Marks | In Y1Q1: 1. Repair and Maintenance Plan (for each school), based on baseline survey in Q1 Thereafter, 2. Implementation of Repair and Maintenance Plan every quarter. As per technical proposal: - Infrastructure repair and maintenance in grouped schools, with SELD's approval | 1. Formally approved Repair and Maintenance Plan, based on Baseline Survey 2. Narrative and evidence (e.g. photographs, or Repair/Maintenance Report) of update on the implementation of the Repair and Maintenance Plan | Y1: Development of R&M Plan with 60 (calendar) days school hand over Y2: ONGOING: Thereafter, report on quarterly basis - repair and maintenance of school infrastructure, facilities and assets during the course of the relevant academic quarter | School repair and maintenance work conducted during the quarter to be provided in a given academic quarter's Quarterly Progress Reports Documentary evidence to be attached as annexures to Quarterly Progress Reports | On-field verification (of maintenance and repair work conducted) by IE's field personnel | i. Major repair and/or maintenance work can only be scheduled during vacations, with prior approval of the SELD. Written requests/applications must be submitted (Copying IE and IA) 30 days prior to vacations, and associated costs must be certified by the Independent Auditor (please see Section 7, pg. 27-28, Concession Agreement) ii. Emergency repair and maintenance work should be undertaken after written intimation to the SELD, as per the requirements of Section 7, pg. 28, Concession Agreement.
|  |  | 6.2 | Meetings and engagement with School Management Committees | 05 Marks | 1. Conducting quarterly SMC meetings Technical Proposal lists the following activities: - SMCs engagement in school management planning, implementation and monitoring. - Annual School Performance Review meetings with SMCs (to share school challenges/achievements) | 1. Due formation of SMCs (General Body and Executive Body) at each school 2. SMC Meeting minutes containing list of SMC members (incl. name, designation, and contact information), points of discussion, and actions, 2. Narrative on SMC meeting agenda points and discussions | Conducting first SMC meeting within 30 days of school handover ONGOING: Therafter, conducting one (01) SMC per month / or every quarter | Narrative/updates on SMC meetings to be provided in a given academic quarter's Quarterly Progress Reports Documentary evidence, Conatect numbers and photgraphs to be attached as annexures to Quarterly Progress Reports | 1. Desk-based review of SMC Meeting minutes and other documentary evidence submitted by EMO (Photographes & Contact numbers of members) 2. On field verification/ observation of SMC on sample basis
|  |  | 6.3 | Improved Community Outreach | 04 Marks | In Y1: 1. Development of Community Outreach Plan (for each school), based on baseline survey along with AMP/SIP / Development of Annual Stakeholders Engagement Plan (including SMB engagements with communities/parents, district education management and administration, PPP-Node, EMOs and school events) Technical Proposal lists the following activities: - Parents engagement in school management planning, implementation and monitoring - Awareness sessions on ECD, child rights, etc., literacy, technical/vocational skill education for parents, adolescents and out of school children. - Monthly parent awareness sessions/Weekly visits to parents by school heads to ensure the schools’ connection with parents and student attendance. Thereafter, 2. Implementation of Community Outreach Plan every quarter | 1. Community Outreach Plan, based on Baseline Survey 2. Narrative and evidence (e.g. photographs, or Field/Community Outreach Report) of updates on the implementation of the Community Outreach Plan | Development of Community Outreach Plan and submission alongwith AMP/SIP for each acadmeic year at the start. ONGOING: Conducting community outreach activities as per Plan and reporitng expected bi-annually as per the CA (ideally one comprehensive community outreach activity in Q1 and Q2, and one in Q3 and Q4) | Narrative/updates on community outreach to be provided in a given academic quarter's Quarterly Progress Reports Documentary evidence to be attached as annexures to Quarterly Progress Reports Only in Q1 nd Q3 | 1. On-field verification (observation) of communuity outreach activities 2. Desk-based review of Field/Community Outreach Reports and other documentary evidence submitted by EMO | i. As per CA, Bi-annual reports (Q1 & Q3) of community outreach to improve student enrolment, attendance and learning needs, to share with them services offered at facilities whoch are beneficial to the community.
|  |  | 6.4 | Parent Teacher Meetings – PTM |  | 1. Conducting PTMs after mid-term and final examinations (summative exams) as per the Concession Agreement | 1. Activity Report 2. Photographs | Within one (01) month of due completion of mid-term and final examinations Bi-annual meetings, especially at the end of the academic term | Narrative/updates on PTMs to be provided in a given academic quarter's Quarterly Progress Reports Documentary evidence to be attached as annexures to Quarterly Progress Reports Only in Q2 and Q4 | 1. On-field verification (observation) of PTMS | i. As per CA, Bi-annual reports (Q2 & Q4) on PTA meetings about progress of their children learning and behavior in the facility.
| 7 | Improved Health and Hygiene Practices, and Sporting Activities | 7.1 | Health and Hygiene practices plan | 03 Marks | In Y1:. 1. Development of H&H Practices Plan of Y1 2. Annual student health screening/ Baseline Y2 onwards 4. Annual student health screening 5. Development of H&H Practices Plan for the academic year | 1. Approved Student Health Screening Reports 2. Formally approved Health and Hygiene Practices Plan with at least one activity based on health and hygiene practices in and outside the facility in each quarter. | 1. Student Health Screening at the beginning of the academic year 2. Development of H&H Practices Plan Within 60 days of AMP On-going: Thereafter quarterly reports on implementation of Plan | Upon completion of Student Health Screening Reports and development of H&H Practices Plan: via email | 1. On-field verification of student screening (observation) 2. Desk-based review of H&H Practices Plan | i. Health and Hygiene Practices Plan with at least one activity based on health and hygiene practices in and outside the facility in each quarter. ii. Baseline of students screening within 2 quarters of the effective date; thereafter annual reporting on screening; Quarterly reporitng on progress achieved.
|  |  | 7.2 | Demonstrated healthy practices of students, supported with health and hygiene activities and facilities | 04 Marks | 1.Implementation of H&H Practices Plan (at least one health-related activity inside, and one activity outside, the school). As per the technical propsoal following activities are expecetd from EMO as part of the H & H plan: - Healthy food events at main schools, parents and students of grouped schools will be invited - SMB Homeopathic college teaching staff will visit schools to provide health consultations and medication - Medical doctors will be engaged for health screenings annually - Hygiene management, first aid and safety trainings for teachers and senior students 2. Regular cleaning/ensuring cleaning of school campus | 1. Narrative and evidence (e.g. photographs, or Activity Report) of updates on the implementation of the H&H Practices Plan | Baseline of students screening within two quarters of the effective date; thereafter annual reporting on screening; Quarterly reporting on progress achieved ONGOING: Implementation of H&H Practices, conducting of health-related activities, and regular cleaning of school facilities during the course of all academic quarters. | Narrative/updates on implementation of H&H Practices Plan, health-related activities and school cleaning to be provided in a given academic quarter's Quarterly Progress Reports Documentary evidence to be attached as annexures to Quarterly Progress Reports | 1. On-field verification of health activities and sporting activities 2. On-field verification of school and facilities' cleanliness | i. Section 7, pg. 30: The EMO is required to hire appropriately trained staff to provide basic health facilities at the schools
|  |  | 7.3 | Sports and Games facility and event plan | 03 Marks | 1. Development of Sports and Games Facility and Event Plan/Co-curricular Activities/ Events Plan 2. Implementation of Plan during the course of all academic quarters/Regular physicial education classes will be part of the time table. As per the technical propsoal following activities are expecetd from EMO as part of the Sports and Games plan: - Main schools will be provided sports materials - Annual sports events will be organized - Extra-curricular activities (science/art festivals, annual result days, national days, cultural days, exposure visits, scouting/girls guide trainings and sports days in constructions schools for children, parents, communities and teachers) 3. Availability and use of relevant sporting goods and articles/Purchase of sports material | 1. Formally approved Sports & Games Facility and Event Plan 2. Narrative and evidence (e.g. photographs, or Activity Report) of updates on implementation of Sports & Games Facility and Event Plan | Development of Sports Plan within 30 days of AMP submission. Thereafter, quarterly reports on implementation of Plan. ONGOING: Implementation of Sports & Games Facility and Event Plan and conducting of sporting activities during the course of all academic quarters. | Upon development of Sports Plan: via email Narrative/updates on implementation of Sports & Games Facility and Event Plan, and sporting activities to be provided in a given academic quarter's Quarterly Progress Reports Documentary evidence to be attached as annexures to Quarterly Progress Reports | 1. Desk-based review of Sports & Games Facility and Event Plan 2. On-field verification of sporting activities and goods/articles
Non-KPIs | 8 | Non-KPIs |  | Non - KPI Activities from Technical/ Financial Porposal |  | Activities as per technical & financial proposal: - Establishment of ECE classes - Hire Master trainers & Assessment expert - Performance based scholarships for private staff for Higher Education - Use of ICT in teaching/administration/monitoring - Tree plantation with students and parents in the community - Development of Project management office - Interns from SMB teachers training institute will be hired for Main schools - Transport service will be part of employment package for staff - Exposure visits, extra-curricular activities for staff and students 4 times a year - subject to savings in respective budget head - Proposed study/exchange tours - Classroom observation-based coaching/training will be provided to teachers by SMB admin staff and Head Masters. - Student Scout Guide groups will be established - Adolescent and Adult Learning and Training Program will be developed at all schools - Stitching classes will be arranged at schools - Provision of support for special needs children - Provision of support for special needs children - Celebration of national and international days (E.g. Mother's day, Father's day, World literacy day, Day of forests, World water day, etc.) - Handyman Training: Technical course for senior students (2 periods/week, subject to PPP-Node, SELD's approval) - Establishment of Science and Computer labs in grouped schools - Provision of solar power at grouped schools - Water Supply Connection / Bore / RO plants to purify drinkng water, will be installed at the schools if required - Formation of student health and environment team - PE period twice a week in main and grouped schools - Procurement of supplementary learning material | Quarterly Reporting | As per AMP/Academic Calender/IF timelines | Narrative/updates in Quarterly Progress Reports | 1. Desk-review 2. Field Verification
|  |  |  | Other Contractual Obligations |  | 1. Handing over reports by EMO after effective date. 2. Annually appraise all employees at the end of each (academic) year, and provide a report to the SELD within thirty (30) days of the end of such year. (Section 7, pg. 31) 3. Implement a safety and surveillance program for the Facility, comply with Safety Regulations and adopt appropriate safeguards and measures for security (Section 7, pg. 27) 4. The EMO is required to submit Quarterly Progress Reports within fifteen (15) days of the end of a given quarter (Section 7, pg. 29) 5. Submission of yearly reports (Section 7, pg. 29) 6. Appoint a Compliance Manager/Contract Manager, as per the requirements set out in Annex 1, (Section 7, Pg. 30) a. The Compliance/Contract Manager shall timely submit reports to the Operator, the Independent Expert and the Authority on weekly, bi-monthly, monthly and quarterly basis. (Annexure 1) b. The Compliance/Contract Manager recommends necessary actions of performance of the terms and conditions of this Agreement to the Operator's management.shareholders and or consortium members in writing so that effective compliance of the agreement is ensured (Annexure 1) c. A meeting is conducted semiannually between the Compliance Manager and the office of the PPP Node on the compliance of terms and conditions of this agreement (Annexure 1)

## OtherImpContractualObligations
Section No. (RFP6) | Description of Provision | Page No. (RFP6) | Page No. (RFP5 for reference)
3 | The EMO shall be free to purchase, at its own cost and expense, assets, equipment or other teaching aids required to be used in the Facility, in particular those that assist the EMO in fulfilling the KPls and/or implementing education philosophy as described in Technical Proposal and Financial Bid of the Project. The EMO shall from time to time also replace the obsolete equipment and assets being used in the Facility with new assets and equipment at its own cost. The Parties further agree that all such assets, equipment or other teaching aids (whether originally provided by SELD or purchasedor replaced by the EMO) shall be the property of the SELD and shall be handed over to SELD, free from any encumbranceson the Transfer Date. | 20 | 14
7 | The EMO will develop and implement a safety and surveillance program for the Facility, comply with Safety Regulations and adopt appropriate safeguards and measures for security | 27 | 21
7 | The EMO can not schedule major repaor or maintenance work at the Facility without prior consent of SELD. Has to be scheduled in vacations, with a 30 day prior notice of details and cost to SELD, IE and IA | 27-28 | 21
7 | Emergency repair and maintenance work should be undertaken after written intimation to the SELD | 28
7 | If EMO ceases operation for 72 consecutive hours, other than forced majeure or unscheduled outage then SELD will step-in and undertake O and M by giving a 24 hour notice | 28 | 22
7 | EMO will maintain records of movable, immovable assets, books, resourcesmachinery, furniture, fixtures, equipment, etc, students, teachers, staff, compliance w KPIs. | 29 | 22
7 | The EMO is required to submit Quarterly Progress Reports within fifteen (15) days of the end of a given quarter | 29 | 22-24
7 | The EMO is required to submit Yearly Reports duly reviewed and certified by the IE within forty-five (45) days of the end of the Academic year to SELD. | 29 | 23
7 | The first two KPI report will not impact the Annuity Payments, but deadlines for completion and submission of deliverables (such as AMP, IF Timelines, Annual SoS, Baseline Surveys) are strict | 30 | 23
7 | The EMO is required to appoint a Compliance Manager/Contract Manager, as per the requirements set out in Annex 1, Concession Agreement. Responsibility: ensure EMO complies w outside regulatory requirments/internal policies/abides by KPIs, terms and conditions, Scope of work in CA. | 30 | 23
7 | The EMO is required to hire appropriately trained staff to provide basic health facilities at the schools | 30 | 24
7 | EMO will ensure key staff is employed on the effective date. If Key staff changes then EMO will prior approval from SELD, replacement has to have same qualification, experience and expertise. Key Staff: Project Director, Compliance Manager, Executive District Coordinator, Education Expert, and Finance Expert. | 31 | 24
7 | The EMO is required to annually appraise all employees at the end of each (academic) year, and provide a report to the SELD within thirty (30) days of the end of such year. | 31 | 25
7 | The EMO will share the Training schedue thirty (30) days prior to the start of such training(s) with all Parties | 32 | 25
7 | The EMO will conduct (2) training sessions each of at least 18 hours for each employee, particularly teaching staff in each financial year. | 32 | 25
7 | All teacher trainings should be ideally scheduled during school vacations (and should not exceed sixty (60) hours in aggregate). Any trainings scheduled in times other than vacations should result in only minimum disruption of teaching and other Services | 32
8 | Within fifteen (15) days of Annuity Amount Payment Evaluation Date, the EMO will submit the QPR to the IE. The IE will issue verified evaluation report within the next fifteen (15) days to the IA. | 33-34 | 27-29
9 | Re-appropriations and budgetary realignments are permitted (except for Management Fees and soft costs, as per the process stipulated herein. Realignment budget will be submitted to the IE and the IA for advice and endorsement. | 36 | 30
14 | EMO will have a meeting within 5 days from the date of FM (Forced Majeaure) reciept w IE for discussion, and where necessary conduct inspections/surveys of the facility to: (a) assess impact (b) determine duration of FM event, (c) formulate damage mitigation measures/steps to resume obligations/performance affected by FM event. | 44 | 38
14 | Timelines will extended of EMO performace due to FM period | 44 | 38-40
14 | IE determines if the EMO can be excused from fulfilling KPIs for the FM period, parties in consultation with IE may revise KPIs in the academic year in the period of FM event | 44
14 | all costs, fees, expenses and charges arising from and relating to the Force Majeure Event shall be allocated in accordance with Article 14.4 | 45
14 | SELD will bare FM costs in occurance of event | 45 | 39
14 | Incase of continuing effect of FM for over 1 quarter, the management fee as per the Annuity Amount Payment Schedule maybe claimed by the Operator subject to the adjustment of such Management Fee (in case adjustment is required) at the end of the FM event. | 45
14 | Save and except as expresslyprovided in this Article 14.4.2,neither Party shall be liable in any mannerwhatsoever to the other Party in respect of any loss, damage, cost, expense, claims, demands and proceedingsrelating to or arising out of occurrenceor existenceof any ForceMajeure Event or exercise of any right pursuant hereto. | 45 | 39
14 | (a) a Force Majeure Event subsists for a continuous period of one hundred and twenty (120) days, either Party may in its discretion Terminate this Agreement by issuing a Termination Notice to the other Party; or (b) in case of a Political Event, theAuthoritydeterminesthat the Force Majeurecosts relating to the same are unacceptable then the Authority may in its discretion Terminate this Agreement by issuinga Termination Notice to the Operator, in upon issue of such termination notice, this agreement shall stand terminated, party issuing the T notice will inform other party of intent and grant 15 days to make representation and then issue T notice. | 45 | 39
14 | SELD will pay termination compensations, as a result of termination in FM event in accordance with article 17 of CA. | 45 | 39
14 | If the Affected Party is rendered wholly or partially unable to perform its obligationsunder this Agreement because of a Force Majeure Event, it shall be excused from performance of such of its obligations (except payment obligations) to the extent it is unable to perform on account of such Force Majeure Event; provided, that: (a) suspension of performace shall be of no greater scope or duration than is required by the FM event and its effects; (b) the Affected Party shall make all reasonable efforts to mitigate or limit damage to the other Party arising out of or as a result of the existence or occurrence of such Force Majeure Event and to cure the same with due diligence; and (c) when the Affected Party is able to resume performance of its obligations under this Agreement, it shall give to the other Party (with a copy to the Independent Expert and the Independent Auditor) notice to that effect and shall promptly resume performance of its obligations hereunder | 45-46 | 39-40
Annex 1 | Annex 1: EMO shall hire services of a Compliance Manager who will be responsible for ensuring that the EMO complies with its outside regulatory requirements and internal policies. He/she will be responsible for making sure that organization abides by the terms and conditions, KeyPerformanceIndicators(KPls) and Scopeof Work under this Concession Agreement. The operator and Authority, in consultation with IE, will develop coordination and/or reporting mechanismfor ensuring complianceof the agreement. Someof the tasks of Compliance/Contract Manager include: i. Compile a checklist formulating that the compliance of the terms of this agreement are duly met within reasonable/ relevant timelines of this agreement; and develop Performa reports for various reportingfrequencies. ii. That the Compliance/ Contract Manager shall timely submit reports to the Operator, the Independent Expert and the Authority on weekly, bi monthly, monthly and quarterly basis. iii. The Compliance/Contract Manager recommends necessary actions of performance of the terms and conditions of this Agreement to the Operator's management.shareholders and or consortium members in writing so that effective compliance of the agreement is ensured. iv. That all submitted reports by the Compliance/ Contract Manager with regards to the performance of the terms and conditions of this Agreement are corroborated with the quarterly reports submitted to the Independent Expert. v. That the Authority reserves its right to recommend removal of the Compliance/Contract Manager appointed by the Operator in case of severe breach of compliance of this agreement. vi. That the Compliance/Contract Manager shall review and advise on SOP's for effective and transparent management of the EMO's roles and responsibilities in terms of the compliance check-list. That a meeting is conducted semi-annually in between the Compliance Manager and the office of the PPP Node on the compliance of terms and conditions of this agreement. | 60
2 | Conditional offer to key staff as detailed in the Technical Bid or any such appointment by the EMO having similar qualifications and experience. Provided that conditional offer of Key Staff will be confirmed on or before the effective date. | 18
4 Point(a) | The EMO shall establish within the first 6 months of the effective, the solar system, the science lab, furniture, and the computer lab facilities as mentioned in the CA and maintain the same to optimum level to ensure that all such utilities are being provided by the Operator uninterrupted for the Concession Period. | 22
4 Point(b) | EMO to Maintain performance security and Sindh Revenue Board registration for the tenure of CA and provide copy to IE, incase of renewal | 22
4 Point(c) | EMO to develop and maintain EMIS which shall be deployed to ensure the performace of its duties as per CA. EMO to Share access with Authority, IE and IA. | 22
4 Point(d) | EMO to develop the Annexure IV (Guidelines for TNA), V (Reporting forms) and XI (Employment Criteria) within timeline, provide copy to Authroity, IE, and IA. | 22
4 Point(e) | All proposed intervantions by the EMO shall be implmeneted as Technical and Financial Bids. | 22
4 Point(g) | EMO will be liable for maintaining the provision of optimim school based staff during the concession period. | 22
4 Point(h) | EMO shall display grievance redressed mechanism on the schools including group of schools notice board along with the respective contact numbers of school & district school administrations, EMOs, and IE, whereby the students and community may get to know the levels through which complains pertaining to school administration, overall learning environment, cleanliness etc. maybe lodged. In case, such complain does not resolve in 7 working days then such complaint may to be reffered to IE by the student or community. | 22
7 | Incase, the no of classrooms are less than the no of grades in the USAID Reconstructed schools, the Authority seeks that additional classrooms should be at par with the specified grades in USAID reconstructed schools. Therefore, either rehabiliatation of the old block where necessary or as a proposed solution the Authority may also allow construction of additional classrooms in such USAID reconstructed schools. For this the EMO is required to submit request to the Authority for the rehabiliatation/construction of additional classrooms with 3 years starting from the effective date. | 28
7 | Incase where the facility has more than the minimum required staff as per the CA and the EMO has the physical space to appoint additional teachers (subject specific and level specific) thereby (exceeding total number of required teachers), the EMO upon approval from the IE maybe allowed for incurring cost against such additonal staff. | 30
9 Point (b) | Under FM the realignment can be proposed on yearly basis as well subject to the cndition that the bid price limit shall remain the same as submitted in the financial bid accpeted by th Authority. | 36
15 | EMO Event of default; failed to remedy the defects specified in the remedial action notice: Achieving less than 75% marks for 2 consecutive quarters except if such marking availed due to permitted events | 47

## Schools
Schools listed in Package 1 (Karachi District)
Cluster/Group Name | School Name | SEMIS Code | Main/Grouped | Taluka
1. Waryo Gabol | GBELS Waryo Gabol | 408180440 | Main | Gadap, Malir
| GBSS Angara | 408180458 | Grouped
2. Sindhi Jamaat Cooperative Housin Society | GBPS Sindhi Jamaat Cooperative Housin Society | 408170153 | Main | Bin Qasim, Malir | Note: | Cluster/Group Name not mentioned in CA
| GBPS Haji Shafi Muhammad Goth | 408170128 | Grouped
| GBPS Master Allahna M. Hassan Panhwar Goth | 408170079 | Grouped
| GBPS Juvenile Jail near Quaidabad Bin Qasim Town | 408170018 | Grouped
3. No. 9 Sector 8/L | GBSS No. 9 Sector 8/L | 408040151 | Main | Orangi
| GGSS No. 14 (Campus) | 408040152 | Grouped
| GGSS No.5 | 408020148 | Grouped
| GGPS No.9 Orangi | 408040031 | Grouped
4. Frontier Colony#1 | GBPS Frontier Colony#1 | 408040062 | Main | Orangi Town
| GBSS Zulfiqar 1C Orangi | 408040149 | Grouped
| Cosmopolitan GGSS (Campus) | 408040156 | Grouped
| GGPSST2 Ali Garh Colony | 408040030 | Grouped
04 Groups/Clusters | 14 Schools | - | - | -