School Education & Literacy Department, Government of Sindh

RFP-6, Package-1, District Karachi Schools being managed by

Sindh Madressah-tul-Islam Board

Quarterly KPIs Progress Report

Period of Performance August 17, 2024 – November 16, 2024

Submitted by:

# Sindh Madressah-tul-Islam Board

(Educational Management Organization)

To:

# Teacher Resource Center

(Independent Expert)

| Basic Details |  |  |  |
| --- | --- | --- | --- |
| RFP No. | RFP 1 RFP 2 RFP 3 RFP 4 RFP 5 RFP 6 RFP 7 RFP 8 RFP 9 RFP 10 |  |  |
| Academic Year | 2024 to 2025 |  |  |
| Year No. | 3 | Quarter No. | 1 |
| Report submitted within time as stipulated in Concession Agreement | 10 Days 15 Days more than 15 Days {please specify the number of days and specify reason for delay} There are various reasons for the delayed reporting, ranging from the backdated issuance of the effective date to the late delivery of furniture. The effective date was August 17, 2022; however, the schools were handed over in February 2023. Additionally, the opening of the ESCROW account experienced a delay of 10 months. Furthermore, the furniture was delivered in May 2023. These were the key reasons that delayed reporting |  |  |
| Name of Schools and SEMIS Code | Construction Schools; Group Schools. - GBELS Waryo Gabol SEMIS Code: 408180440; 1.1. GBSS Angara SEMIS Code: 408180458. 2. GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153; 2.1. GBPS Haji Shafi Muhammad Goth SEMIS Code: 408170128 2.2. GBPS Master Allahna Muhammad Hassan Panhwer Goth SEMIS Code: 408170079 2.3. GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018. 3. GBSS No. 9 Sector 8/L SEMIS Code: 408040151; 3.1. GGSS No 14 (Campus) SEMIS Code: 408040152 3.2. GGSS No 5 SEMIS Code: 408020148 3.3. GGPS No-09 Orangi SEMIS Code: 408040031. 4. GBPS Frontier Colony No. 1 SEMIS Code:; 4.1. GBSS Zulfiqar 1 C Orangi SEMIS Code: 408040149 4.2. GGSS Cosmopolitan (Campus) SEMIS Code: 408040156 4.3. GGPS ST 2 Ali Garh Colony SEMIS Code: 408040030. |
| Name of District | Sukkur Larkana Khairpur Kamber Shahdadkot Dadu Karachi-Malir, West, South Other |  |  |
| RFP# and District Package Name | RFP 6, District Package 1, Karachi |  |  |
| No. of SBEP schools and group schools | SBEP Schools= 4 Group Schools= 10 |  |  |

Contents

Sindh Madressah-tul-Islam Board	1

Teacher Resource Center	1

List of Acronyms	1

Performance Summary of each KPIs	2

Reporting on Key Performance Indicators (KPIs)	2

KPI 1: School Management Plan	3

a.	Annual Management Plan (AMP)	3

b.	Implementation Framework (IF)	3

c.	Development/Functioning of Education Management Information System (EMIS)	3

KPI 2: Improved Staff Availability and Attendance	3

a.	Availability of Staff	3

b.	Functional Attendance Management	13

c.	Staff Attendance	13

KPI 3: Improved Student Enrolment, Attendance, and Retention	21

a.	Student Enrolment, Attendance Management, and Retention Plan	21

b.	Improvement in Student Enrolment, Attendance Management, and Retention Rates	21

KPI 4: Lesson Planning and Student Assessment System	46

a.	Annual Scheme of Studies (Not Applicable for RFP 1)	46

b.	Lesson Planning	46

c.	Formative Assessments (In-House)	46

d.	Summative Assessments (Internal)	46

e.	Summative Assessments (External)	46

KPI 5: Continuous Professional Development of Staff	47

a.	Staff Trainings	47

b.	Quality Assurance of CPD Sessions	48

KPI 6: School Repair and Maintenance; Community Engagement	48

a.	Repair and Maintenance of Schools within the Group/Cluster	48

b.	Meetings with School Management Committee (SMC)	48

c.	Improved Community Outreach	48

d.	Parent-Teacher Meetings (PTMs)	49

KPI 7: Improved Health and Hygiene Practices	49

a.	Health and Hygiene Activities	49

b.	Student Sports and Extra-Curricular Activities	49

Non-KPIs	50

Reporting formats developed as per Concession Agreement deliverables	51

Notice of Annuity Amount Payment	51

Conclusions	51

Challenges and Red Flags	51

Lessons Learned	51

Annexure	52

Annexure 1 [Complain Regarding Furniture]	Error! Bookmark not defined.

Annexure 2 [EMIS Data]	Error! Bookmark not defined.

Annexure 3 [Shortage of Teachers]	Error! Bookmark not defined.

Annexure 4 [Angara Goth School Building]	Error! Bookmark not defined.

Annexure 5 [Lesson Plans]	Error! Bookmark not defined.

Annexure 6 [CPD of Teaching and Non-Teaching Staff]	Error! Bookmark not defined.

Annexure 7 [SMC Meetings and Minutes of Meeting]	Error! Bookmark not defined.

Annexure 8 [Parent Teacher Meetings]	Error! Bookmark not defined.

Annexure 9 [Health and Hygiene Activities]	Error! Bookmark not defined.

# List of Acronyms

AMP		Annual Management Plan

EMIS		Education Management Information System

EMO		Educational Management Organization

HT		Head Teacher

IA		Independent Auditor

IE		Independent Expert

KPI		Key Performance Indicator

PPP Node 	Public Private Partnership Node

PTM		Parent-Teacher Meeting

SMB		Sindh Madressah tul Islam Board

SMC		School Management Committee

# Performance Summary of each KPIs

1. School Management Plan

The School Management Plan was submitted on 6th March 2023 and activities were conducted as per the plan. Major activities planned for the quarter were Final Term Examination and Result day.

2. Improved Staff Availability and Attendance

The staff availability challenge in most of the schools in terms of STR is completed. The EMO appointed teachers. However, the SNE of the schools were revised as per STR and level of schools and teachers were provided by the authority. However, staff attendance improved in the reporting quarter.

3. Improved Students' Enrolment, Attendance and Retention

The EMO conducted meeting with SMC to improve the strength of the students and performance of the students during the academic year.

- Students' Assessment System

Final Term Examination was conducted in order to see the performance of the students and teachers

- Continuous Professional Development (CPD)

Teachers were observed by the coordinators and HM to fill the teachers need analysis tool. This will help us to identify the learners' needs, desires and prerequisites

6. School Repair and Maintenance and Improved Community Engagement

The repair and maintenance was done in June and July like repairing of fans, winding of gate, doors and windows were installed.

- Improved Health and Hygiene Practices and Sporting Activities

Not applicable in this quarter

# Reporting on Key Performance Indicators (KPIs)

## KPI 1: School Management Plan

### Annual Management Plan (AMP)

The AMP was submitted in the start of the academic year. However, it is not applicable in the current quarter.

- Implementation Framework (IF)

The IF was submitted in the start of the academic year. However, it is not applicable in the current quarter.

### Development/Functioning of Education Management Information System (EMIS)

The EMIS was to be developed by the SMB; however, after the PPP Node started its own centralized EMIS, they conducted orientation for all EMOs and directed us to upload data to that centralized system. Therefore, a separate dedicated EMIS has not been developed yet due to a lack of clarity on whether we need to manage two parallel systems (EMIS) or only upload data to the EMIS developed by the PPP Node. This clarification is yet to be received from the PPP Node. In the meantime, we have been persistently uploading data as per the instructions of the PPP Node. On the other hand, we will be updating our data on excel sheet for the evidence

## KPI 2: Improved Staff Availability and Attendance

### Availability of Staff

Details of teacher availability for each school are provided in the table below. Teaching Staff Available in Schools. School Name; Government / Private; Teaching / Non- Teaching; Subjects / Department; Categories (SST, ST, PST, etc.); Active (regular); Transfer In; Deputation; New Hiring; Total. GBELS Waryo Gabol; Govt/Private; Teaching; HSTs= 0 JSTs= 3 JESTs= 1 ECT= 1 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=3 Private 4; 12; 0; 0; 0; 12. GBSS Angara; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 3 ECT= 0 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=3 Private 0; 6; 0; 0; 0; 6. GBPS Sindhi Jamaat Cooperative Housing Society; Govt/Private; Teaching; HSTs= 1 JSTs= 1 JESTs= 0 ECT= 1 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=6 No. of Private teachers= 9; 15; 0; 0; 0; 15. GBPS Haji Shafi Muhammad Goth; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 0 ECT= 0 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=5 Private 0; 4; 0; 0; 0; 4. GBPS Master Allahna Muhammad Hassan Panhwer Goth; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 0 ECT= 1 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=7 Private= 0; 8; 0; 0; 0; 8. GBPS Juvinail Jail near Quaidabad Bin Qasim Town; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 0 ECT= 0 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=3 Private 0; 5; 0; 0; 0; 5. GBSS No. 9 Sector 8/L; Govt/Private; Teaching; HSTs= 9 JSTs= 4 JESTs= 5 ECT= 1 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=12 Private 1; 32; 0; 0; 0; 32. GGSS No 14 (Campus); Govt/Private; Teaching; HSTs= 8 JSTs= 5 JESTs= 4 ECT= 0 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=0 Private= 0; 17; 0; 0; 0; 17. GGSS No 5; Govt/Private; Teaching; HSTs= 9 JSTs= 3 JESTs= 6 ECT= 0 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=0 Private= 0; 18; 0; 0; 0; 18. GGPS No-09 Orangi; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 0 ECT= 1 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=10; 11; 0; 0; 0; 11. GBPS Frontier Colony No. 1; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 0 ECT= 1 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=12 Private=2; 12; 0; 0; 3; 15. GBSS Zulfiqar 1 C Orangi; Govt/Private; Teaching; HSTs= 2 JSTs= 1 JESTs= 5 ECT= 0 O.T= 0 PET= 0 SLT= 1 WI= 0 ITT=0 PST=0 Private= 0; 4; 0; 0; 5; 9. GGSS Cosmopolitan (Campus); Govt/Private; Teaching; HSTs= 9 JSTs= 1 JESTs= 15 ECT= 0 O.T= 0 PET= 0 SLT= 1 WI= 0 ITT=0 PST=12 Private=0; 37; 0; 0; 1; 31. GGPS ST 2 Ali Garh Colony; Govt/Private; Teaching; HSTs= 0 JSTs= 0 JESTs= 0 ECT= 0 O.T= 0 PET= 0 SLT= 0 WI= 0 ITT=0 PST=4 Private=1; 5; 0; 0; 1; 6. Details of availability of non-teaching staff for each school are provided in the table below. Non-Teaching Staff Available in School. School Name; Government / Private; Teaching / Non- Teaching; Subjects / Department; Categories (SST, ST, PST, etc.); Active (regular); Transfer In; Deputation; New Hiring; Total. GBELS Waryo Gabol; Govt/Private; Non-Teaching; ---; ---; 8; 0; 0; 0; 8. GBSS Angara; Govt/Private; Non-Teaching; ------; ------; 0; 0; 0; 0; 0. GBPS Sindhi Jamaat Cooperative Housing Society; Govt/Private; Non-Teaching; ------; ------; 9; 0; 0; 0; 9. GBPS Haji Shafi Muhammad Goth; Govt/Private; Non-Teaching; Primary; -----; 2; 0; 0; 0; 0. GBPS Master Allahna Muhammad Hassan Panhwer Goth; Govt/Private; Non-Teaching; Primary; -------; 2; 0; 0; 0; 0. GBPS Juvinail Jail near Quaidabad Bin Qasim Town; Govt/Private; Non-Teaching; Primary; -----; 2; 0; 0; 0; 1. GBSS No. 9 Sector 8/L; Govt/Private; Non-Teaching; Secondary; -------; 9; 0; 0; 0; 9. GGSS No 14 (Campus); Govt/Private; Non-Teaching; Secondary; 5; 0; 0; 0; 5. GGSS No 5; Govt/Private; Non-Teaching; Secondary; ----; 4; 0; 0; 0; 4. GGPS No-09 Orangi; Govt/Private; Non-Teaching; Primary; -----; 2; 0; 0; 0; 2. GBPS Frontier Colony No. 1; Govt/Private; Non-Teaching; Primary; ----; 6; 0; 0; 0; 6. GBSS Zulfiqar 1 C Orangi; Govt/Private; Non-Teaching; Secondary; -----; 5; 0; 0; 0; 5. GGSS Cosmopolitan (Campus); Govt/Private; Non-Teaching; Secondary; -----; 9; 0; 0; 0; 9. GGPS ST 2 Ali Garh Colony; Govt/Private; Non-Teaching; Primary; ------; 2; 0; 0; 0; 2. Staff Leaves Status Teaching Staff; Non-Teaching Staff. School Name; Type of Leaves; No. of staff; Type of Leaves; No. of staff. 8L; Casual Leave; Casual Leave. GGSS 14; Casual Leave; 10; Casual Leave; 0. GGSS 5; Casual Leave; 12; Casual Leave; 0. GGPS 9; Casual Leave; 8; Casual Leave; 0. Frontier; Casual Leave; 12; Casual Leave; 0. Zulfiqar; Casual Leave; 0; Casual Leave; 0. Cosmopolitan; Casual Leave; 0; Casual Leave; 0. Qasba ST 2; Casual Leave; 0; Casual Leave; 10. Waryo; Casual Leave; 0; Casual Leave; 0. Angara; Casual Leave; 0; Casual Leave; 0. Sindhi Jamat; Casual Leave; 7; Casual Leave; 1. Shafi Muhammad; Casual Leave; 0; Casual Leave; 0. Hassan Panwar; Casual Leave; 0; Casual Leave; 0. Junivail Jail; Casual Leave; 0; Casual Leave; 0. Student Teacher Ratio Most of the schools are facing a shortage of teachers (details of the school-wise STR are provided in the table below). In its technical proposal, the SMB committed to providing teachers at the early level, while the authority is responsible for providing teachers as per the revised SNE. However, due to the late handover of the schools, the SNE approval was delayed. The SMB team had frequent meetings with the DEOs of the relevant districts to revise the SNE according to the level of the schools and student enrolment. In this connection, the SMB also held a joint meeting with the District Support team at the DEO office in Malir, where the issue of the lack of teaching staff was raised. The SMB was informed that the proposal for the revision of the SNE has been sent to the Secretary SE&LD. The PPP Node assured us that they would pursue the case and get the required SNE approved. However, the SNE has not yet been revised, and teachers have not been provided as per the STR. Additionally, the SMB wrote a letter (a copy of the letter is enclosed as Annexure 3) to the PPP Node requesting the provision of teachers, but the problem has not been resolved yet. Moreover, the SMB has appointed teachers in all schools, and the details of the number of teachers appointed are as follows: The SMB has appointed seven teachers at GBPS Sindhi Jamaat Cooperative Housing Society, four teachers at GBELS Waryo Gabol, two teachers at GBPS Frontier Colony No. 1, and one teacher at GBSS No. 9 Sector 8/L. Here are the details of student teacher ratio for each school. Student Teacher Ratio (STR). School Name; Class / Grade; STR. 1. GBELS Waryo Gabol; ECE to VIII; 35:1. - GBSS Angara; VI to X; 36:1. - GBPS Sindhi Jamaat Cooperative Housing Society; ECE to IX; 31:1. - GBPS Haji Shafi Muhammad Goth; ECE to V; 47:1. - GBPS Master Allahna Muhammad Hassan Panhwer Goth; ECE TO V; 67:1. - GBPS Juvenile Jail near Quaidabad Bin Qasim Town; ECE TO V; 36:1. - GBSS No. 9 Sector 8/L; ECE TO X; 26:1. - GGSS No 14 (Campus); VI TO XI; 23:1. - GGSS No 5; VI TO X; 47:1. - GGPS No-09 Orangi; ECE TO V; 66:1. - GBPS Frontier Colony No. 1; ECE TO V; 25:1. - GBSS Zulfiqar 1 C Orangi; VI TO X; 56:1. - GGSS Cosmopolitan (Campus); ECE TO X; 28:1. - GGPS ST 2 Ali Garh Colony; ECE TO V; 45:1.

### Functional Attendance Management

Currently attendance is being taken through Biometric system in all schools of all Government employees. However, all the current government and private teaching and non-teaching staff are also marking attendance in teachers’ attendance register manually. Due to delay in handing over all the things have been mismanaged and not able to meet the timeline

### Staff Attendance

Individual staff attendance has not been maintained on excel sheet. It will be furnished from the next quarter. This section presents the descriptive analysis of attendance of teaching staff for the reporting quarter in comparison with the previous quarter and baseline. The same data is also reported in the table below. - GBELS Waryo Gabol - Baseline Attendance: 82% - Previous Quarter: 85% - Current Attendance: 92.6% - Analysis: The attendance has remained stable with no change over the quarters. - GBSS Angara - Baseline Attendance: 16% - Previous Quarter: 32% - Current Attendance: 52% - Analysis: There has been a remarkable improvement in attendance, increasing from non-existent at baseline to 32%. This suggests successful interventions or changes that significantly boosted student attendance. - The school is in deplorable condition with very dangerous condition. For reference pictures of the schools’ building are annexed for reference and better understanding of the situation. - GBPS Sindhi Jamaat Cooperative Housing Society - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 98% - Analysis: Attendance has been consistently high. The school has maintained an almost perfect attendance rate. - GBPS Haji Shafi Muhammad Goth - Baseline Attendance: 99% - Previous Quarter: 85% - Current Attendance: 95% - Analysis: The attendance improved from the baseline to a peak in the previous quarter and then decreased by 6%. Nonetheless, it remains very high. - GBPS Master Allahna Muhammad Hassan Panhwer Goth - Baseline Attendance: 99% - Previous Quarter: 87% - Current Attendance: 96% - Analysis: Similar to the previous school, this school saw an increase from the baseline to almost perfect attendance, with a slight decrease in the current quarter. - GBPS juvenile Jail near Quaidabad Bin Qasim Town - Baseline Attendance: 85% - Previous Quarter: 50% - Current Attendance: 95% - Analysis: Attendance saw a dramatic increase from the baseline to the previous quarter - GBSS No. 9 Sector 8/L - Baseline Attendance: 85% - Previous Quarter: 92.66% - Current Attendance: 100% - Analysis: The school showed an increase from the baseline to the previous quarter, followed by a decrease in the current quarter. - GGSS No 14 (Campus) - Baseline Attendance: 91% - Previous Quarter: 91% - Current Attendance: 100% - Analysis: Attendance increased from the baseline to the previous quarter and slightly decreased to 4%, still indicating strong attendance. - GGSS No 5 - Baseline Attendance: 90% - Previous Quarter: 87.6% - Current Attendance: 98% - Analysis: There was a decrease of 4% from the baseline to the previous quarter. - GGPS No-09 Orangi - Baseline Attendance: 98% - Previous Quarter: 92% - Current Attendance: 95% - Analysis: Attendance remained constant at an excellent rate of 98%, indicating strong and stable attendance. - GBPS Frontier Colony No. 1 - Baseline Attendance: 90% - Previous Quarter: 89.5% - Current Attendance: 83.78% - Analysis: Attendance decrease significantly to the previous quarter and then returned to the baseline rate. This suggests possible short-term improvements or interventions. - GBSS Zulfiqar 1 C Orangi - Baseline Attendance: 88% - Previous Quarter: 93% - Current Attendance: 87% - Analysis: Attendance remained constant. - GGSS Cosmopolitan (Campus) - Baseline Attendance: 88% - Previous Quarter: 91% - Current Attendance: 90% - Analysis: Attendance decreased slightly. - GGPS ST 2 Ali Garh Colony - Baseline Attendance: 92% - Previous Quarter: 89% - Current Attendance: 89% - Analysis: Attendance remained constant from the previous quarter. Summary of Key Trends: - Significant Improvements: Schools like GBSS Angara and GBPS Juvenile Jail near Quaidabad Bin Qasim Town have shown substantial improvements in attendance, indicating effective interventions or improvements in school management. - High and Stable Attendance: Schools such as GGPS No-09 Orangi, GBPS Sindhi Jamaat Cooperative Housing Society, and GBSS Zulfiqar 1 C Orangi have maintained consistently high attendance rates. - Fluctuating Attendance: Some schools, such as GBPS Frontier Colony No. 1 and GGSS No 5, experienced fluctuations but generally maintained good attendance rates. - Slight Decreases: A few schools saw minor decreases in attendance, which may warrant closer monitoring to ensure they do not indicate emerging issues. Teaching Staff Attendance Percentage. School Name; Month; Baseline Attendance; Attendance in the previous quarter; Current Attendance. GBELS Waryo Gabol; May 2024 to Aug 2024; 82%; 85%; 92.6%. GBSS Angara; May 2024 to Aug 2024; 16%; 32%; 52%. GBPS Sindhi Jamaat Cooperative Housing Society; May 2024 to Aug 2024; 100%; 100%; 98%%. GBPS Haji Shafi Muhammad Goth; May 2024 to Aug 2024; 99%; 85%; 95%. GBPS Master Allahna Muhammad Hassan Panhwer Goth; May 2024 to Aug 2024; 99%; 87%; 96%. GBPS Juvinail Jail near Quaidabad Bin Qasim Town; May 2024 to Aug 2024; 85%; 50%; 95%. GBSS No. 9 Sector 8/L; May 2024 to Aug 2024; 85%; 85%; 82.6%. GGSS No 14 (Campus); May 2024 to Aug 2024; 91%; 95%; 91%. GGSS No 5; May 2024 to Aug 2024; 90%; 91%; 87.6%. GGPS No-09 Orangi; May 2024 to Aug 2024; 98%; 98%; 92%. GBPS Frontier Colony No. 1; May 2024 to Aug 2024; 90%; 89.5%; 83.78%. GBSS Zulfiqar 1 C Orangi; May 2024 to Aug 2024; 88%; 93%; 87%. GGSS Cosmopolitan (Campus); May 2024 to Aug 2024; 88%; 91%; 90%. GGPS ST 2 Ali Garh Colony; May 2024 to Aug 2024; 92%; 89%; 89%. Analysis of Non-Teaching Staff Attendance for the reporting quarter in comparison with the previous quarter and baseline data. - GBELS Waryo Gabol - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 100% - Analysis: Attendance has been consistently perfect at 100% across all periods, indicating exceptional attendance management and student commitment. - GBSS Angara - Baseline Attendance: 10% - Previous Quarter: 61% - Current Attendance: 61% - Analysis: This school has shown a significant improvement in attendance, increasing from a very low baseline of 10% to 60%. This indicates successful intervention strategies or improvements in school conditions. - GBPS Sindhi Jamaat Cooperative Housing Society - Baseline Attendance: 100% - Previous Quarter: 99% - Current Attendance: 99% - Analysis: Attendance remains consistently perfect at 100%, showcasing strong attendance policies and adherence. - GBPS Haji Shafi Muhammad Goth - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 97% - Analysis: Consistently perfect attendance of 100% across all periods, reflecting highly effective attendance practices. - GBPS Master Allahna Muhammad Hassan Panhwer Goth - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 99% - Analysis: Perfect attendance has been maintained throughout, indicating no attendance issues. - GBPS Juvenile Jail near Quaidabad Bin Qasim Town - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 100% - Analysis: The school has maintained perfect attendance, suggesting effective student engagement and attendance enforcement. - GBSS No. 9 Sector 8/L - Baseline Attendance: 75% - Previous Quarter: 100% - Current Attendance: 94% - Analysis: Attendance is sustained. - GGSS No 14 (Campus) - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 99% - Analysis: Attendance has remained perfect at 100% throughout, reflecting consistent attendance management. - GGSS No 5 - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 98% - Analysis: Perfect attendance maintained, indicating excellent attendance tracking and student participation. - GGPS No-09 Orangi - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 100% - Analysis: Attendance has been consistently at 100%, demonstrating strong student attendance and effective management. - GBPS Frontier Colony No. 1 - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 99% - Analysis: The school has maintained perfect attendance, reflecting no attendance-related challenges. - GBSS Zulfiqar 1 C Orangi - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 100% - Analysis: Perfect attendance has been consistent across all periods, showing strong adherence to attendance policies. - GGSS Cosmopolitan (Campus) - Baseline Attendance: 100% - Previous Quarter: 100% - Current Attendance: 99% - Analysis: Attendance remains perfect, indicating no attendance issues and effective management. - GGPS ST 2 Ali Garh Colony - Baseline Attendance: 90% - Previous Quarter: 90% - Current Attendance: 91% - Analysis: Attendance has remained stable at 90%, suggesting consistent but slightly lower than perfect attendance, which may warrant minor improvements. Summary of Key Trends: - Perfect Attendance: The majority of schools have maintained a perfect attendance rate of 100% consistently over the baseline, previous quarter, and current attendance periods. This reflects highly effective attendance policies, student engagement, and possibly external support mechanisms. - Significant Improvement: GBSS Angara is a notable case with a substantial increase in attendance from 10% to 60%, indicating successful interventions or changes that have significantly impacted student attendance positively. - Consistent High Attendance: GGPS ST 2 Ali Garh Colony has consistently maintained a 90% attendance rate, indicating stable but not perfect attendance. This stability suggests good practices, though there may be room for slight improvement to reach 100%. Non-Teaching Staff Attendance Percentage. School Name; Month; Baseline Attendance; Attendance in the previous quarter; Current Attendance. GBELS Waryo Gabol; May 2024 to Aug 2024; 100%; 100%; 100%. GBSS Angara; May 2024 to Aug 2024; 10%; 61%; 61%. GBPS Sindhi Jamaat Cooperative Housing Society; May 2024 to Aug 2024; 100%; 99%; 99%. GBPS Haji Shafi Muhammad Goth; May 2024 to Aug 2024; 100%; 100%; 97%. GBPS Master Allahna Muhammad Hassan Panhwer Goth; May 2024 to Aug 2024; 100%; 100%; 998%. GBPS Juvinail Jail near Quaidabad Bin Qasim Town; May 2024 to Aug 2024; 100%; 100%; 100%. GBSS No. 9 Sector 8/L; May 2024 to Aug 2024; 71%; 100%; 100%. GGSS No 14 (Campus); May 2024 to Aug 2024; 100%; 100%; 99%. GGSS No 5; May 2024 to Aug 2024; 100%; 100%; 98%. GGPS No-09 Orangi; May 2024 to Aug 2024; 100%; 100%; 100%. GBPS Frontier Colony No. 1; May 2024 to Aug 2024; 100%; 100%; 99%. GBSS Zulfiqar 1 C Orangi; May 2024 to Aug 2024; 100%; 100%; 100%. GGSS Cosmopolitan (Campus); May 2024 to Aug 2024; 100%; 100%; 99%. GGPS ST 2 Ali Garh Colony; May 2024 to Aug 2024; 90%; 90%; 91%.

## KPI 3: Improved Student Enrolment, Attendance, and Retention

### Student Enrolment, Attendance Management, and Retention Plan

In order to improve students’ attendance and retention, meetings were held with the SMC members and community members where the importance of regular attendance was reiterated. The community members and parents were informed about the Government policy of dropping out student after three months consecutive absence. In addition to this, meetings were held with the head masters regarding ensuring authentic attendance and filtering out the dropped-out students. A number of events were organized in all schools to emphasize the importance of attendance which are listed below.

### Improvement in Student Enrolment, Attendance Management, and Retention Rates

As per government order, the final examination started from 17 April 2024 to 24 April 2024. After the examination ended, the students were given off as the schools were selected for Board centers. The result was announced in all the schools at the end of May. We start new admissions in June 2024. An entry test was conducted for selecting new students.No changes occurred in the current quarter as it was the end of the session, no new admissions were taken and neither were the students dropout.

| Enrollment Status (GBSS No. 9 Sector 8/L SEMIS Code: 408040151) Disaggregated by Gender & Grade |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Grade | Initial baseline (at time of handing over) |  | Current baseline (at start of academic year) |  | Current enrolment (at the end of reporting period) |  | Percentage of improvement (from initial baseline) |  | Percentage of improvement (from current baseline) |  |
|  | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys |
| ECE | 0 | 0 | 0 | 0 | 13 | 36 | -55% | 0% | #DIV/0! | #DIV/0! |
| KGI | 0 | 0 | 18 | 18 | 18 | 29 | #DIV/0! | #DIV/0! | 0% | 61% |
| KGII | 0 | 0 | 0 | 0 | 12 | 29 |  | #DIV/0! | #DIV/0! | #DIV/0! |
| I | 55 | 60 | 4 | 4 | 18 | 35 | -67% | -42% | 350% | 775% |
| II | 47 | 45 | 36 | 41 | 50 | 42 | 6% | -7% | 39% | 2% |
| III | 38 | 37 | 42 | 37 | 72 | 54 | 89% | 46% | 71% | 46% |
| IV | 50 | 52 | 25 | 15 | 44 | 41 | -12% | -21% | 76% | 173% |
| V | 41 | 29 | 17 | 35 | 24 | 30 | -41% | 3% | 41% | -14% |
| VI | 40 | 32 | 27 | 30 | 38 | 35 | -5% | 9% | 41% | 17% |
| VII | 35 | 38 | 24 | 32 | 43 | 40 | 23% | 5% | 79% | 25% |
| VIII | 38 | 30 | 19 | 21 | 31 | 23 | -18% | -23% | 63% | 10% |
| IX | 25 | 19 | 17 | 30 | 19 | 35 | -24% | 84% | 12% | 17% |
| X | 12 | 48 | 25 | 16 | 24 | 16 | 100% | -67% | -4% | 0% |
| Enrollment Status of (GBPS Frontier Colony No. 1 SEMIS Code: 408040062) Disaggregated by Gender & Grade |  |  |  |  |  |  |  |  |  |  |
| Grade | Initial baseline (at time of handing over) |  | Current baseline (at start of academic year) |  | Current enrolment (at the end of reporting period) |  | Percentage of improvement (from initial baseline) |  | Percentage of improvement (from current baseline) |  |
|  | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys |
| ECE | 12 | 25 | 12 | 25 | 9 | 13 | -25% | -48% | -48% | -48% |
| I | 22 | 26 | 22 | 26 | 40 | 35 | 82% | 35% | 35% | 35% |
| II | 50 | 38 | 50 | 38 | 26 | 26 | -48% | -32% | -32% | -32% |
| III | 23 | 25 | 23 | 25 | 24 | 21 | 4% | -16% | -16% | -16% |
| IV | 31 | 36 | 31 | 36 | 23 | 21 | -26% | -42% | -42% | -42% |
| V | 34 | 34 | 34 | 34 | 22 | 22 | -35% | -35% | -35% | -35% |
| VI | 0 | 0 | 42 | 31 | 22 | 18 | 21% | 13% | -42% | -42% |
| VII | 0 | 0 | 31 | 20 | 31 | 20 | 0% | 0% | 0% | 0% |
| Enrollment Status of (GBSS Zulfiqar 1 C Orangi SEMIS Code: 408040149) Disaggregated by Gender & Grade |  |  |  |  |  |  |  |  |  |  |
| Grade | Initial baseline (at time of handing over) |  | Current baseline (at start of academic year) |  | Current enrolment (at the end of reporting period) |  | Percentage of improvement (from initial baseline) |  | Percentage of improvement (from current baseline) |  |
|  | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys |
| VI |  | 16 |  | 16 |  | 16 |  | 0% |  | 0% |
| VII |  | 18 |  | 18 |  | 27 |  | 50% |  | 50% |
| VIII |  | 17 |  | 17 |  | 27 |  | 59% |  | 59% |
| IX |  | 35 |  | 35 |  | 50 |  | 43% |  | 43% |
| X |  | 72 |  | 72 |  | 73 |  | 1% |  | 1% |
| Enrollment Status of (GGSS No 14 (Campus) SEMIS Code: 408040152) Disaggregated by Gender & Grade |  |  |  |  |  |  |  |  |  |  |
| Grade | Initial baseline (at time of handing over) |  | Current baseline (at start of academic year) |  | Current enrolment (at the end of reporting period) |  | Percentage of improvement (from initial baseline) |  | Percentage of improvement (from current baseline) |  |
|  | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys |
| VI | 100 | 98 | 70 | 4 | 86 | 98 | -14% | -96% | 23% | 2350% |
| VII | 96 | 76 | 68 | 40 | 94 | 76 | -2% | -47% | 38% | 90% |
| VIII | 112 | 83 | 140 | 50 | 142 | 83 | 27% | -40% | 1% | 66% |
| IX | 132 | 51 | 112 | 31 | 122 | 51 | -8% | -39% | 9% | 65% |
| X | 99 | 92 | 100 | 60 | 114 | 92 | 15% | -35% | 14% | 53% |
| XI | 11 | 0 | 11 | 0 | 11 | 0 | 0% | #DIV/0! | 0% | #DIV/0! |
| Enrollment Status of (GGSS No 5 SEMIS Code: 408020148) Disaggregated by Gender & Grade |  |  |  |  |  |  |  |  |  |  |
| Grade | Initial baseline (at time of handing over) |  | Current baseline (at start of academic year) |  | Current enrolment (at the end of reporting period) |  | Percentage of improvement (from initial baseline) |  | Percentage of improvement (from current baseline) |  |
|  | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys |
| VI | 137 |  | 137 |  | 137 |  | 0% |  | 0% |  |
| VII | 112 |  | 112 |  | 112 |  | 0% |  | 0% |  |
| VIII | 127 |  | 127 |  | 127 |  | 0% |  | 0% |  |
| IX | 99 |  | 99 |  | 99 |  | 0% |  | 0% |  |
| X | 151 |  | 151 |  | 151 |  | 0% |  | 0% |  |
| Enrollment Status of (GGPS No-09 Orangi SEMIS Code: 408040031) Disaggregated by Gender & Grade |  |  |  |  |  |  |  |  |  |  |
| Grade | Initial baseline (at time of handing over) |  | Current baseline (at start of academic year) |  | Current enrolment (at the end of reporting period) |  | Percentage of improvement (from initial baseline) |  | Percentage of improvement (from current baseline) |  |
|  | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys | Girls | Boys |
| ECE | 76 | 36 | 76 | 36 | 48 | 50 | -37% | 39% | -37% | 39% |
| I | 25 | 23 | 25 | 23 | 52 | 43 | 108% | 87% | 108% | 87% |
| II | 36 | 22 | 36 | 22 | 44 | 42 | 22% | 91% | 22% | 91% |
| III | 54 | 25 | 54 | 25 | 40 | 47 | -26% | 88% | -26% | 88% |
| IV | 79 | 26 | 79 | 26 | 80 | 35 | 1% | 35% | 1% | 35% |
| V | 80 | 20 | 80 | 20 | 108 | 34 | 35% | 70% | 35% | 70% |

Enrollment Status of (GGPS ST 2 Ali Garh Colony SEMIS Code: 408040030) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. ECE; 37; 30; 37; 30; 42; 63; 14%; 110%; 14%; 110%. I; 31; 30; 31; 30; 28; 40; -10%; 33%; -10%; 33%. II; 30; 26; 30; 26; 20; 27; -33%; 4%; -33%; 4%. III; 27; 25; 27; 25; 20; 30; -26%; 20%; -26%; 20%. IV; 30; 24; 30; 24; 25; 29; -17%; 21%; -17%; 21%. V; 25; 18; 25; 18; 17; 25; -32%; 39%; -32%; 39%. Enrollment Status of (GGSS Cosmopolitan (Campus) SEMIS Code: 408040156) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. ECE; 0; 0; 0; 0; 54; 0; #DIV/0!; #DIV/0!; 0%; 0%. I; 100; 40; 100; 40; 36; 34; -64%; -15%; -64%; -15%. II; 34; 31; 34; 31; 50; 36; 47%; 16%; 47%; 16%. III; 40; 26; 40; 26; 50; 29; 25%; 12%; 25%; 12%. IV; 20; 30; 20; 30; 46; 31; 130%; 3%; 130%; 3%. V; 30; 24; 30; 24; 45; 30; 50%; 25%; 50%; 25%. VI; 83; 57; 83; 57; 95; 55; 14%; -4%; 14%; -4%. VII; 72; 58; 72; 58; 87; 60; 21%; 3%; 21%; 3%. VIII; 87; 46; 87; 46; 80; 75; -8%; 63%; -8%; 63%. IX; 91; 63; 91; 63; 140; 85; 54%; 35%; 54%; 35%. X; 87; 40; 87; 40; 91; 63; 5%; 58%; 5%; 58%. Enrollment Status of (GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. KG; 13; 16; 21; 15; 21; 15; 8%; 25%; 25%; 25%. 1; 4; 10; 11; 20; 11; 20; 150%; 20%; 20%; 20%. 2; 5; 16; 5; 9; 5; 9; 100%; 13%; 13%; 13%. 3; 6; 12; 4; 9; 4; 9; 33%; 25%; 25%; 25%. 4; 7; 8; 1; 7; 1; 7; 57%; 38%; 38%; 38%. 5; 2; 11; 4; 5; 4; 5; 150%; 9%; 9%; 9%. Enrollment Status of (Sindhi Jamat) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. KG; 0; 0; 49; 61; 53; 64; 50%; 50%; 7%; 7%. 1; 11; 12; 22; 27; 24; 32; 100%; 125%; 17%; 17%. 2; 10; 19; 26; 26; 26; 26; 100%; 100%; 0%; 0%. 3; 15; 17; 24; 28; 24; 28; 100%; 100%; 0%; 0%. 4; 16; 16; 31; 22; 31; 22; 38%; 44%; 92%; 92%. 5; 18; 19; 23; 23; 23; 23; 39%; -16%; 33%; 33%. 6; 0; 0; 25; 17; 25; 17; #DIV/0!; #DIV/0!; 155%; 155%. 7; 0; 0; 17; 29; 17; 29; #DIV/0!; #DIV/0!; 30%; 30%. 8; 0; 0; 23; 19; 23; 19; #DIV/0!; #DIV/0!; #DIV/0!; #DIV/0!. 9; 0; 0; 18; 17; 18; 17; #DIV/0!; #DIV/0!; #DIV/0!; #DIV/0!. Enrollment Status of (GBPS Shafi Muhammad) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. KG; 16; 18; 34; 43; 34; 43; 25%; 72%; 55%; 55%. 1; 15; 17; 25; 25; 25; 25; 67%; 47%; 32%; 32%. 2; 19; 12; 28; 18; 28; 18; 32%; 50%; -18%; -18%. 3; 15; 11; 6; 12; 6; 12; 20%; 73%; 12%; 12%. 4; 16; 13; 10; 10; 10; 10; 19%; 62%; 17%; 17%. 5; 14; 17; 10; 14; 10; 14; 7%; -12%; 50%; 50%. Enrollment Status of (GBPS Hassan Panhwar) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. KG; 20; 20; 127; 138; 127; 138; 0%; 55%; 55%; 55%. 1; 33; 15; 18; 19; 25; 25; -24%; 67%; 32%; 32%. 2; 26; 13; 18; 22; 25; 18; -4%; 38%; -18%; -18%. 3; 34; 33; 15; 17; 18; 19; -47%; -42%; 12%; 12%. 4; 25; 23; 8; 18; 19; 21; -24%; -9%; 17%; 17%. 5; 24; 27; 10; 10; 15; 15; -38%; -44%; 50%; 50%. Enrollment Status of (GBPS Waryo Gabol) Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. KG; 0; 0; 0; 0; 20; 31; #DIV/0!; #DIV/0!; #DIV/0!; #DIV/0!. 1; 33; 35; 18; 19; 25; 25; -24%; -29%; 32%; 32%. 2; 26; 33; 18; 22; 25; 18; -4%; -45%; -18%; -18%. 3; 32; 22; 15; 17; 18; 19; -44%; -14%; 12%; 12%. 4; 28; 26; 8; 18; 19; 21; -32%; -19%; 17%; 17%. 5; 27; 27; 10; 10; 15; 15; -44%; -44%; 50%; 50%. 6; 32; 22; 18; 17; 18; 19; -44%; -14%; 12%; 12%. 7; 28; 26; 11; 18; 19; 21; -32%; -19%; 17%; 17%. 8; 27; 27; 10; 10; 15; 15; -44%; -44%; 50%; 50%. Enrollment Status of Angara Goth Disaggregated by Gender & Grade. Grade; Initial baseline (at time of handing over); Current baseline (at start of academic year); Current enrolment (at the end of reporting period); Percentage of improvement (from initial baseline); Percentage of improvement (from current baseline). Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. KG; 13; 16; 13; 16; 14; 20; 8%; 25%; 25%; 25%. 1; 4; 10; 4; 10; 10; 12; 150%; 20%; 20%; 20%. 2; 5; 16; 5; 16; 10; 18; 100%; 13%; 13%; 13%. 3; 6; 12; 6; 12; 8; 15; 33%; 25%; 25%; 25%. 4; 7; 8; 7; 8; 11; 11; 57%; 38%; 38%; 38%. 5; 2; 11; 2; 11; 5; 12; 150%; 9%; 9%; 9%. - Any new admissions and drop-outs recorded during the Reporting Period, disaggregated by School, grade and gender; New Admissions & Drop-outs Status of (GBSS No. 9 Sector 8/L SEMIS Code: 408040151) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. ECE; 0; 0; 0; 0. KGI; 0; 0; 0; 0. KG II; 0; 0; 0; 0. I; 0; 0; 0; 0. II; 0; 0; 2; 0. III; 0; 0; 2; 4. IV; 0; 0; 0; 2. V; 0; 0; 3; 5. VI; 0; 0; 9; 8. VII; 0; 0; 1; 8. VIII; 0; 0; 1; 0. IX; 0; 0; 0; 0. X; 0; 0; 0; 0. New Admissions & Drop-outs Status of (GGSS No 14 (Campus) SEMIS Code: 408040152) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. VIA; 0; 0; 0; 0. VIB; 0; 0; 0; 0. VIIA; 0; 0; 0; 6. VIIB; 0; 0; 0; 0. VIIIA; 0; 0; 0; 0. VIIIB; 0; 0; 0; 0. VIIIC; 0; 0; 0; 0. IXA; 0; 0; 0; 0. IXB; 0; 0; 0; 0. IXC; 0; 0; 0; 0. XA; 0; 0; 0; 2. XB; 0; 0; 4; 6. XC; 0; 0; 0; 0. XI; 0; 0; 0; 0. New Admissions & Drop-outs Status of (GGPS No-09 Orangi SEMIS Code: 408040031) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. ECE; 0; 0; 0; 0. I; 0; 0; 0; 0. II; 0; 0; 0; 0. III; 0; 0; 0; 0. IV; 0; 0; 0; 22. V; 0; 0; 0; 0. New Admissions & Drop-outs Status of (GBPS Frontier Colony No. 1 SEMIS Code: 408040062) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. ECE; 9; 13; 0; 0. I; 4; 1; 0; 0. II; 3; 2; 0; 0. III; 4; 3; 0; 0. IV; 4; 1; 0; 0. V; 2; 2; 0; 0. VI; 3; 2; 0; 0. VII; 1; 1; 0; 0. New Admissions & Drop-outs Status of (GBSS Zulfiqar 1 C Orangi SEMIS Code: 408040149) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. VI; 0; 0. VII; 0; 0. VIII; 0; 0. IX; 0; 0. X; 0; 0. New Admissions & Drop-outs Status of (GGPS ST 2 Ali Garh Colony SEMIS Code: 408040030) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. ECE; 0; 0; 0; 0. I; 0; 0; 0; 0. II; 0; 0; 0; 0. III; 0; 0; 0; 3. IV; 0; 0; 1; 0. V; 0; 0; 1; 4. New Admissions & Drop-outs Status of (GGSS Cosmopolitan (Campus) SEMIS Code: 408040156) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. ECE; 0; 0; 0; 0. I; 0; 0; 1; 0. II; 0; 0; 0; 0. III; 0; 0; 0; 0. IV; 0; 0; 0; 0. V; 0; 0; 0; 0. VI; 0; 0; 1; 0. VII; 0; 0; 0; 1. VIII; 0; 0; 1; 1. IX; 0; 0; 0; 0. X; 0; 0; 0; 0. New Admissions & Drop-outs Status of (GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. KG; 16; 9; 0; 0. I; 4; 5; 10; 10. II; 0; 0; 0; 1. III; 3; 3; 4; 6. IV; 0; 1; 3; 9. V; 0; 0; 5; 3; Promote to Secondary Class. New Admissions & Drop-outs Status of (GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Boys; Girls; Boys; Girls. ECE; 53; 64; 0; 0. I; 1; 3; 1; 4. II; 0; 3; 0; 0. III; 2; 1; 0; 0. IV; 5; 2; 0; 0. V; 4; 1; 0; 0. VI; 1; 4; 0; 0. VII; 3; 6; 1; 0. VIII; 9; 6; 1; 1. IX; 12; 13; 0; 1. New Admissions & Drop-outs Status of (GBPS Shafi Muhammad) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. KG; 0; 0; 0; 0. I II; 0; 0; 0; 0. III; 0; 0; 0; 0. IV; 0; 0; 0; 0. V; 0; 0; 9; 11; Promote to Secondary Class. New Admissions & Drop-outs Status of (GBPS Hassan Panhwar) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. KG; 0; 0; 0; 0. I II; 0; 0; 0; 0. III; 0; 0; 0; 0. IV; 0; 0; 0; 0. V; 0; 0; 11; 15; Promote to Secondary Class. New Admissions & Drop-outs Status of (GBPS Waryo Gabol) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. KG; 0; 0; 0; 0. I II; 0; 0; 0; 0. III; 0; 0; 0; 0. IV; 0; 0; 0; 0. V; 0; 0; 0; 0. New Admissions & Drop-outs Status of (GBPS Angara Goth) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. KG; 0; 0; 0; 0. I II; 0; 0; 0; 0. III; 0; 0; 1; 1. IV; 0; 0; 0; 3. V; 0; 0; 0; 0. New Admissions & Drop-outs Status of (GGSS School No 5) Disaggregated by Gender & Grade. Grade; No. of New Admissions; No. of dropouts; Reason of high drop outs (If applicable). Girls; Boys; Girls; Boys. KG; 0; 0; 0; 0. I II; 0; 0; 0; 0. III; 0; 0; 1; 1. IV; 0; 0; 0; 3. V; 0; 0; 0; 0. - Student Attendance Pictures of attendance registers are attached as a separate file for reference. However, an Excel sheet detailing individual attendance has not been prepared; it will be shared starting next quarter. Aggregate attendance of students has been compiled and analyzed, and the findings are presented below, school-wise and class-wise. Students Attendance Percentage of (GBSS No. 9 Sector 8/L SEMIS Code: 408040151) Disaggregated by Gender & Grade. Grade; Month # JUNE; Month #JULY; Month AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. KGI; Off; OFF; Off; OFF; Off; OFF. KGII; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. 6; Off; OFF; Off; OFF; Off; OFF. 7; Off; OFF; Off; OFF; Off; OFF. 8; Off; OFF; Off; OFF; Off; OFF. 9; Off; OFF; Off; OFF; Off; OFF. 10; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018) Disaggregated by Gender & Grade. Grade; Month #AUG; Month #SEP; MONTH # OCT; MONTH # NOV. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBPS Haji Shafi Muhammad Goth SEMIS Code: 408170128) Disaggregated by Gender & Grade. Grade; Month #AUG; Month #SEP; Month #OCT; Month #NOV. Girls; Boys; Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBPS Master Allahna Muhammad Hassan Panhwer Goth SEMIS Code: 408170079) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GGPS ST 2 Ali Garh Colony SEMIS Code: 408040030) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GGPS No-09 Orangi SEMIS Code: 408040031) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GGSS No 14 (Campus) SEMIS Code: 408040152) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. VI; Off; OFF; Off; OFF; Off; OFF. VII; Off; OFF; Off; OFF; Off; OFF. VIII; Off; OFF; Off; OFF; Off; OFF. IX; Off; OFF; Off; OFF; Off; OFF. X; Off; OFF; Off; OFF; Off; OFF. XI; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GGSS No 5 SEMIS Code: 408020148) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. VI; Off; Off; Off. VII; Off; Off; Off. VIII; Off; Off; Off. IX; Off; Off; Off. X; Off; Off; Off. Students Attendance Percentage of (GGSS Cosmopolitan (Campus) SEMIS Code: 408040156) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. 6; Off; OFF; Off; OFF; Off; OFF. 7; Off; OFF; Off; OFF; Off; OFF. 8; Off; OFF; Off; OFF; Off; OFF. 9; Off; OFF; Off; OFF; Off; OFF. 10; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBPS Sindhi Jamat) Disaggregated by Gender & Grade. Grade; Month #SEP; Month #OCT; Month # NOV. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; 79%; 74%; 75%; 82%; 83%; 73%. 5; 78%; 88%; 67%; 84%; 81%; 90%. 6; 81%; 85%; 75%; 80%; 88%; 83%. 7; 49%; 79%; 95%; 71%; 85%; 80%. 8; 97%; 62%; 85%; 85%; 88%; 78.6%. 9; 94%; 74%; 70%; 84%; 80%; 85%. Students Attendance Percentage of (GBPS Frontier Colony no. 1 Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. 6; Off; OFF; Off; OFF; Off; OFF. 7; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBSS Zulfiqar School) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. VI; OFF; OFF; OFF. VII; OFF; OFF; OFF. VIII; OFF; OFF; OFF. IX; OFF; OFF; OFF. X; OFF; OFF; OFF. Students Attendance Percentage of (GBPS Waryo Gabol) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. ECE; Off; OFF; Off; OFF; Off; OFF. 1; Off; OFF; Off; OFF; Off; OFF. 2; Off; OFF; Off; OFF; Off; OFF. 3; Off; OFF; Off; OFF; Off; OFF. 4; Off; OFF; Off; OFF; Off; OFF. 5; Off; OFF; Off; OFF; Off; OFF. 6; Off; OFF; Off; OFF; Off; OFF. 7; Off; OFF; Off; OFF; Off; OFF. 8; Off; OFF; Off; OFF; Off; OFF. Students Attendance Percentage of (GBPS Angara Goth) Disaggregated by Gender & Grade. Grade; Month #JUNE; Month #JULY; Month #AUG. Girls; Boys; Girls; Boys; Girls; Boys. VI; Off; OFF; Off; OFF; Off; OFF. VII; Off; OFF; Off; OFF; Off; OFF. VIII; Off; OFF; Off; OFF; Off; OFF. IX; Off; OFF; Off; OFF; Off; OFF. X; Off; OFF; Off; OFF; Off; OFF. - Comparison of current attendance percentage (grade and gender wise) with previous quarter; Comparison of Students Attendance Percentage of (GBELS Waryo Gabol SEMIS Code: 408180440) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 64%; 68%; OFF; OFF. KGI; 62%; 77%; OFF; OFF. KGII; 34%; 43%; OFF; OFF. 1; 64%; 66%; OFF; OFF. 2; 62%; 72%; OFF; OFF. 3; 71%; 67%; OFF; OFF. 4; 65%; 66%; OFF; OFF. 5; 61%; 60%; OFF; OFF. 6; 62%; 65%; OFF; OFF. 7; 64%; 62%; OFF; OFF. 8; 62%; 55%; OFF; OFF. 9; 60%; 69%; OFF; OFF. 10; 62%; 69%; OFF; OFF. Total; 65%; 66%; OFF; OFF. Comparison of Students Attendance Percentage of (GBPS Master Allahna Muhammad Hassan Panhwer Goth SEMIS Code: 408170079) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 50%; 70%; OFF; OFF. 1; 67%; 68%; OFF; OFF. 2; 50%; 59%; OFF; OFF. 3; 54%; 60%; OFF; OFF. 4; 59%; 89%; OFF; OFF. 5; 48%; 65%; OFF; OFF. Total; 64%; 68.50%; OFF; OFF. Comparison of Students Attendance Percentage of (GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 64%; 62%; OFF; OFF. 1; 62%; 64%; OFF; OFF. 2; 62%; 67%; OFF; OFF. 3; 77%; 79%; OFF; OFF. 4; 74%; 65%; OFF; OFF. 5; 63%; 53%; OFF; OFF. 6; 51%; 62%; OFF; OFF. 7; 51%; 73%; OFF; OFF. 8; 63%; 72%; OFF; OFF. Total; 63%; 66.33%. Comparison of Students Attendance Percentage of (GBPS Haji Shafi Muhammad Goth SEMIS Code: 408170128) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 65%; 60%; OFF; OFF. 1; 54%; 68%; OFF; OFF. 2; 60%; 69%; OFF; OFF. 3; 60%; 60%; OFF; OFF. 4; 79%; 69%; OFF; OFF. 5; 65%; 65%; OFF; OFF. Total; 63%; 65.16%. Comparison of Students Attendance Percentage of (GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 60%; 50%. 1; 58%; 58%. 2; 50%; 59%. 3; 54%; 70%. 4; 69.3%; 69%. 5; 58%; 65%. Total; 58%; 62%. Comparison of Students Attendance Percentage of (GBSS No. 9 Sector 8/L SEMIS Code: 408040151) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 54%; 63%; OFF; OFF. KGI; 40%; 77%; OFF; OFF. KGII; 44%; 63%; OFF; OFF. 1; 44%; 56%; OFF; OFF. 2; 52%; 72%; OFF; OFF. 3; 61%; 67%; OFF; OFF. 4; 65%; 56%; OFF; OFF. 5; 61%; 60%; OFF; OFF. 6; 62%; 64%; OFF; OFF. 7; 64%; 67%; OFF; OFF. 8; 62%; 65%; OFF; OFF. 9; 69%; 69%; OFF; OFF. 10; 66%; 69%; OFF; OFF. Total; 57%; 65%. Comparison of Students Attendance Percentage of (GBPS Frontier Colony No. 1 SEMIS Code: 408040062) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 55%; 60%; OFF; OFF. 1; 64%; 68%; OFF; OFF. 2; 50%; 59%; OFF; OFF. 3; 60%; 60%; OFF; OFF. 4; 69%; 69%; OFF; OFF. 5; 65%; 65%; OFF; OFF. Total; 61%; 64%. Comparison of Students Attendance Percentage of (GGPS ST 2 Ali Garh Colony SEMIS Code: 408040030) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 75%; 60%; OFF; OFF. 1; 58%; 58%; OFF; OFF. 2; 64%; 49%; OFF; OFF. 3; 65%; 50%; OFF; OFF. 4; 69%; 69%; OFF; OFF. 5; 57%; 65%; OFF; OFF. Total; 65%; 58.5%. Comparison of Students Attendance Percentage of (GBSS Angara SEMIS Code: 408180458) Disaggregated by Gender & Grade The condition of the school is very poor. It was stated in the proposal that the school requires complete reconstruction. Parents are reluctant to send their children because the building is unsafe. Pictures of the school building are attached as Annexure- 4. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. VI; 10%; 7%; OFF; OFF. VII; 5%; 6%; OFF; OFF. VIII; 6%; 2%; OFF; OFF. IX; 5%; 0%; OFF; OFF. X; 2%; 7%; OFF; OFF. Total; 5.6%; 4%. Comparison of Students Attendance Percentage of (GGSS No 14 (Campus) SEMIS Code: 408040152) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. VI; 72%; 64.5%; OFF; OFF. VII; 70%; 50%; OFF; OFF. VIII; 73%; 54%; OFF; OFF. IX; 75%; 43%; OFF; OFF. X; 69%; 41%; OFF; OFF. Total; 71%; 50.4%. Comparison of Students Attendance Percentage of (GGPS No-09 Orangi SEMIS Code: 408040031) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. VI; 55; OFF. VII; 57; OFF. VIII; 68%; OFF. IX; 64%; OFF. X; 61%; OFF. Total; 61%. Comparison of Students Attendance Percentage of (GGSS No 5 SEMIS Code: 408020148) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. VI; 63%; 34%; OFF; OFF. VII; 68%; 35%; OFF; OFF. VIII; 63%; 44%; OFF; OFF. IX; 65%; 29%; OFF; OFF. X; 60%; 29%; OFF; OFF. Total; 64%; 34%. Comparison of Students Attendance Percentage of (GBSS Zulfiqar 1 C Orangi SEMIS Code: 408040149) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. VI; 44.5%; OFF. VII; 35%; OFF. VIII; 27%; OFF. IX; 21%; OFF. X; 32%; OFF. Total; 33.8%. Comparison of Students Attendance Percentage of (GGSS Cosmopolitan (Campus) SEMIS Code: 408040156) Disaggregated by Gender & Grade. Grade; Previous Quarter Attendance (%); Current Attendance (%). Girls; Boys; Girls; Boys. ECE; 40%; 42%; OFF; OFF. 1; 27%; 49%; OFF; OFF. 2; 52%; 65%; OFF; OFF. 3; 68%; 67%; OFF; OFF. 4; 67%; 52%; OFF; OFF. 5; 58%; 61%; OFF; OFF. 6; 43%; 57%; OFF; OFF. 7; 55%; 71%; OFF; OFF. 8; 64%; 62%; OFF; OFF. 9; 65%; 65%; OFF; OFF. 10; 58%; 48%; OFF; OFF. Total; 54.27%; 58%. As the first day was the orientation period and students were practicing for Independence day so the attendance was not satisfactory. Students Retention Percentage of (GBSS No. 9 Sector 8/L SEMIS Code: 408040151). Baseline (Number / % retained); Previous quarter (Number / % retained). 70%; 100%. Students Retention Percentage of (GGSS No 14 (Campus) SEMIS Code: 408040152). Baseline (Number / % retained); Previous quarter (Number / % retained). 81%; 100%. Students Retention Percentage of (GGSS No 5 SEMIS Code: 408020148). Baseline (Number / % retained); Previous quarter (Number / % retained). 80%; 100%. Students Retention Percentage of (GGPS No-09 Orangi SEMIS Code: 408040031). Baseline (Number / % retained); Previous quarter (Number / % retained). 82%; 100%. Students Retention Percentage of (GBPS Frontier Colony No. 1 SEMIS Code: 408040062). Baseline (Number / % retained); Previous quarter (Number / % retained). 80%; 100%. Students Retention Percentage of (GBSS Zulfiqar 1 C Orangi SEMIS Code: 408040149). Baseline (Number / % retained); Previous quarter (Number / % retained). 78%; 100%. Students Retention Percentage of (GGPS ST 2 Ali Garh Colony SEMIS Code: 408040030). Baseline (Number / % retained); Previous quarter (Number / % retained). 80%; 100%. Students Retention Percentage of (GGSS Cosmopolitan (Campus) SEMIS Code: 408040156). Baseline (Number / % retained); Previous quarter (Number / % retained). 76%; 100%. Students Retention Percentage of (GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153). Baseline (Number / % retained); Previous quarter (Number / % retained). 83%; 100%. Students Retention Percentage of (GBPS Haji Shafi Muhammad Goth SEMIS Code: 408170128). Baseline (Number / % retained); Previous quarter (Number / % retained). 83%; 100%. Students Retention Percentage of (GBPS Master Allahna Muhammad Hassan Panhwer Goth SEMIS Code: 408170079). Baseline (Number / % retained); Previous quarter (Number / % retained). 86%; 100%. Students Retention Percentage of (GBPS Juvenile Jail Quaidabad B. Qasim SEMIS Code: 408170018). Baseline (Number / % retained); Previous quarter (Number / % retained). 50%; 100%. Students Retention Percentage of (GBELS Waryo Gabol SEMIS Code: 408180440). Baseline (Number / % retained); Previous quarter (Number / % retained). 80%; 100%. Students Retention Percentage of (GBSS Angara SEMIS Code: 408180458). Baseline (Number / % retained); Previous quarter (Number / % retained). 50%; 55%.

## KPI 4: Lesson Planning and Student Assessment System

### Annual Scheme of Studies (Not Applicable for RFP 1)

Not applicable in this quarter as it is submitted already at the start of the quarter.

### Lesson Planning

The lesson plans are prepared by the teachers themselves. The lesson plans were prepared and implemented by the teachers appointed by the EMO. However, there has been resistance from the government teachers regarding the preparation and implementation of lesson plans in almost all schools. A syllabus breakup was provided to all teachers, class-wise and subject-wise (see the annexure 5). The lesson plans are made by the teachers on a weekly basis and are checked against the SOS, syllabus breakup, and daily diary by the coordinators and HM. There has been resistance from most of the government teachers in preparing and implementing lesson plans. To overcome this problem, a training session was planned where all teachers were oriented on the importance of lesson planning and taught how to develop lesson plans. Consequently, the teachers appointed by the EMO have been preparing and implementing the lesson plans, but the government teachers remain reluctant to follow this practice. To address this issue, the EMO plans to conduct more capacity-building sessions for all teachers so they can adopt this practice.

### Formative Assessments (In-House)

Final term Examination was conducted from class 4 to 8.

### Summative Assessments (Internal)

Class 9th and 10th students appeared in SSC Board examinations.

### Summative Assessments (External)

| Board result has not been announced yet. School Name GBSS 8L. SAT Results; Annual Board Examinations. Last year/before EMO’s Operations; Current year; Last year before EMO’s Operations /; Current year. |
| --- |
| School Name GBSS 14 |  |  |  |
| SAT Results |  | Annual Board Examinations |  |  |
| Last year/before EMO’s Operations | Current year | Last year before EMO’s Operations / | Current year |  |
| School Name GGSS 5 |  |  |  |
| SAT Results |  | Annual Board Examinations |  |  |
| Last year/before EMO’s Operations | Current year | Last year before EMO’s Operations / | Current year |  |
| School Name GBSS Zulfiqar |  |  |  |
| SAT Results |  | Annual Board Examinations |  |  |
| Last year/before EMO’s Operations | Current year | Last year before EMO’s Operations / | Current year |  |
| School Name GBSS Cosmopolitan |  |  |  |
| SAT Results |  | Annual Board Examinations |  |  |
| Last year/before EMO’s Operations | Current year | Last year before EMO’s Operations / | Current year |  |

## KPI 5: Continuous Professional Development of Staff

### Staff Trainings

| Not applicable in this quarter. During this period compliance manager and coordinators conducted one to one meeting session with all the staff to know about the challenges they faced during the last academic year and assigned them the time table for new session. During this activity we also come to know about their expertise and weakness which helped us to fill TNA tool. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name, (Main/Group School) |  | Staff Name (all school staff) | Major Training Need Assessment (TNA) Areas | Trainings provided before reporting period | Training organized during reporting period |  |

## KPI 6: Repair and Maintenance; Community Engagement

### Repair and Maintenance of Schools within the Group/Cluster Repair and maintenance was done in different schools School name; Planned activity; Status in the reporting quarter. 8L; Wiring issues, fans repairing, windows and doors installation; Done. Frontier; Wiring issues; Done. Sindhi Jamat; Sewerage line repairing,; Done. Waryo Gabol; Wiring issues; Done.

### Meetings with School Management Committee (SMC)

School Name; Key Agendas of Meeting; Venue and Date; Key Actions Points. 8L; Admission campaign,discussion on building issues and security; GBSS 8L school 12th Aug 2024; For admission campaign students and teachers survey the area.. Frontier; Admission campaign,discussion on building issues and security; GBSS 8L school 12th Aug 2024; For admission campaign students and teachers survey the area.. Waryo Gabol; Admission campaign,discussion on building issues and security; GBSS 8L school 12th Aug 2024. Sindhi Jamat; Not done as HM was transferred..

### Improved Community Outreach

Not applicable in this quarter.

School name; Planned activity; Status in the reporting quarter; Date of Activity; Description of Activity.

### Parent-Teacher Meetings (PTMs)

School Name; Agendas; Date; No. of Participation. 8L; Mid Term Examination Result; 5 Jan 2024; 600. Frontier; Mid Term Examination Result; 5 Jan 2024; 250. Sindhi Jamat; Mid Term Examination Result; 5 Jan 2024; 300. Waryo; Mid Term Examination Result; 5 Jan 2024; 200.

## KPI 7: Improved Health and Hygiene Practices

### Health and Hygiene Activities

Not applicable in this quarter

School name; Planned activity; Status in the reporting quarter; Date of Activity; Description of Activity.

### Student Sports and Extra-Curricular Activities

Not applicable in this quarter

School name; Planned activity; Status in the reporting quarter; Date of Activity; Description of Activity.

# Non-KPIs

Please provide details about the following for each school (including main and group schools):

- Planned School-wise (including main and grouped schools for RFP 4-5) Non-KPI activities as per the technical and financial proposal, AMP and Academic Calendar

- School-wise activities conducted in the reporting quarter (Include details such as date and description of each activity in each school)

- Entry test was conducted, Result day celebration, Independence Day Celebration, Distribution of sanitary material and stationeries(planners, attendance registers teachers and students, daily diary students and teachers, stock register)

- If an activity was not conducted, please state reasoning.

- All these activities were conducted. Evidences available in school

- Please provide evidence such as pictures for each activity in each school.

# Reporting formats developed as per Concession Agreement deliverables

| S. No | Annexures | Description of Annexures | Whether developed within stipulated time | Implemented in letter and spirit |
| --- | --- | --- | --- | --- |
| 1 | IV | Guideline for the capacity test |  |  |
| 2 | V | Reporting forms Types: |  |  |
| 3 | XI | Employment Criteria |  |  |

# Notice of Annuity Amount Payment

- [Provide activity detail]

- [was detected by Compliance Manager in case of RFP#4 and 5]

- Organization response if any to para 2

- [Status]

# Conclusions

## Challenges and Red Flags

List noteworthy challenges faced during the Reporting Period, and any strategies implemented to address these challenges. (Not limited to 5 challenges)

- Shortage of books is one of the main important problems in providing good quality education and completing the syllabus.

- Some government teaching and non teaching staff are not cooperating with the EMO.

- Some old building are in a bad condition.

- Security issue is one of the basic problem in running the schools properly.

## Lessons Learned

Provide briefs on lessons learned by EMO during the Reporting Period

- How to improve school system.

- How to enhance the quality of education

- How to manage the school system in order to achieve goals

# Annexure

(Evidence & supporting documents for KPI tasks and activities completed such as Training participants list, SMC meeting participants list and minutes, government notifications, formal letters of EMO addressed to the Authority etc.)

- In all our constructed schools, furniture is incomplete, and the quality of the furniture is too bad

- The computer lab is not properly working as the sockets are not according to the cables.

- Due to wiring problem in the school the solar system is not working properly.

# Events

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

Happy Teachers Day

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

Eid Milad-Un-Nabi

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

Assessment

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

Parents Teacher Meeting (PTM)

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

6 September Defense Day

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

Mango Day

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

14 August Independence Day

GBPS Sindhi Jamaat Cooperative Housing Society SEMIS Code: 408170153

Health Screening Day